## Title Page
Submitted: 1/12/2023
Approved: 1/12/2023
| First Name | Last Name | Office/Title | Phone Number | E-mail
Responsible Officer | John | Gardner | ASMO | 301-225-3822 | john.l.gardner22.civ@army.mil
Primary Contact | John | Gardner | ASMO | 301-225-3822 | john.l.gardner22.civ@army.mil
Alternate Contact | Prasanna | Satarasinghe | ASMO | 301-225-3781 | prasanna.j.satarasinghe.civ@army.mil
Alternate Contact | Stevan | Jovancevic | ASMO | 301-225-3774 | stevan.jovancevic.civ@army.mil
Note: In order to receive SRF funding for efforts prior to the auction, this federal entity has agreed that it will provide (I) to the fullest extent possible, for sharing and coordination of eligible frequencies with non-Federal users, including reasonable accommodation by the eligible Federal entity for the use of eligible frequencies by non-Federal users during the period that the entity is relocating its spectrum uses (in this clause referred to as the ‘‘transition period’’); and (II) for non-Federal users to be able to use eligible frequencies during the transition period in geographic areas where the eligible Federal entity does not use such frequencies. Additionally, this eligible Federal entity will, during the transition period, make itself available for negotiation and discussion with non-Federal users not later than 30 days after a written request therefor; and during the transition period, make available to a non-Federal user with appropriate security clearances any classified information (as defined in section 798(b) of title 18) regarding the relocation process, on a need-to-know basis, to assist the non-Federal user in the relocation process with such eligible Federal entity or other eligible Federal entities. [47 U.S.C. § 928(d)(3)(B)(ii)]

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth (MHz) | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Frequency Remarks | Geographic Location associated with Timeline (AAO in this column indicates the timeline is associated with the geographic location defined by the Authorized Area of Operation in the frequency assignment) | Sharing Type (Indefinite, Temporary i.e. Coordinated, or None) | Temporary Sharing Timeline (Months After 1/14/2022) | Indefinite Sharing Timeline (Months After 1/14/2022) | Vacate Assignment Timeline (Months After 1/14/2022)
AR100505 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | KS | ***** | ***** | KS | ***** | ***** |  | AoA | Indefinite |  | 9
AR111214 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | MD | ***** | ***** | MD | ***** | ***** |  | AoA | Indefinite |  | 9
AR111215 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | MD | ***** | ***** | MD | ***** | ***** |  | AoA | Indefinite |  | 9
AR111216 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | MD | ***** | ***** | MD | ***** | ***** |  | AoA | Indefinite |  | 9
AR130606 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | CO | ***** | ***** | CO | ***** | ***** |  | AoA | Indefinite |  | 9
AR135167 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | NC | ***** | ***** | NC | ***** | ***** |  | AoA | Indefinite |  | 9
AR135702 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | OK | ***** | ***** | OK | ***** | ***** |  | AoA | Indefinite |  | 9
AR141406 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | WA | ***** | ***** | WA | ***** | ***** |  | AoA | Indefinite |  | 9
AR141412 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | WA | ***** | ***** | WA | ***** | ***** |  | AoA | Indefinite |  | 9
AR141683 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | CO | ***** | ***** | CO | ***** | ***** |  | AoA | Indefinite |  | 9
AR145359 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | GA | ***** | ***** | GA | ***** | ***** |  | AoA | Indefinite |  | 9
AR145365 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | TN | ***** | ***** | TN | ***** | ***** |  | AoA | Indefinite |  | 9
AR145371 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | MS | ***** | ***** | MS | ***** | ***** |  | AoA | Indefinite |  | 9
AR145392 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | GA | ***** | ***** | GA | ***** | ***** |  | AoA | Indefinite |  | 9
AR151409 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | OH | ***** | ***** | OH | ***** | ***** |  | AoA | Indefinite |  | 9
AR152600 | AN/TPQ-53 | ***** | 3500 | ***** | 0 | Fixed Radar | ***** | NM | ***** | ***** | NM | ***** | ***** |  | AoA | Indefinite |  | 9
AR155115 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | KY | ***** | ***** | KY | ***** | ***** |  | AoA | Indefinite |  | 9
AR155432 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | NY | ***** | ***** | NY | ***** | ***** |  | AoA | Indefinite |  | 9
AR155433 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | NY | ***** | ***** | NY | ***** | ***** |  | AoA | Indefinite |  | 9
AR155434 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | NY | ***** | ***** | NY | ***** | ***** |  | AoA | Indefinite |  | 9
AR155438 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | VA | ***** | ***** | VA | ***** | ***** |  | AoA | Indefinite |  | 9
AR155439 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | VA | ***** | ***** | VA | ***** | ***** |  | AoA | Indefinite |  | 9
AR155440 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | VA | ***** | ***** | VA | ***** | ***** |  | AoA | Indefinite |  | 9
AR155445 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | VT | ***** | ***** | VT | ***** | ***** |  | AoA | Indefinite |  | 9
AR155446 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | VT | ***** | ***** | VT | ***** | ***** |  | AoA | Indefinite |  | 9
AR155450 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | PA | ***** | ***** | PA | ***** | ***** |  | AoA | Indefinite |  | 9
AR155451 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | PA | ***** | ***** | PA | ***** | ***** |  | AoA | Indefinite |  | 9
AR155452 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | PA | ***** | ***** | PA | ***** | ***** |  | AoA | Indefinite |  | 9
AR174079 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | ID | ***** | ***** | ID | ***** | ***** |  | AoA | Indefinite |  | 9
AR184066 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | MN | ***** | ***** | MN | ***** | ***** |  | AoA | Indefinite |  | 9
AR192454 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | NM | ***** | ***** | NM | ***** | ***** |  | AoA | Indefinite |  | 9
AR192455 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | NM | ***** | ***** | NM | ***** | ***** |  | AoA | Indefinite |  | 9
AR192730 | AN/TPQ-53 | ***** | 3500 | ***** | 0 | Fixed Radar | ***** | AZ | ***** | ***** | AZ | ***** | ***** |  | AoA | Indefinite |  | 9
AR194107 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | UT | ***** | ***** | UT | ***** | ***** |  | AoA | Indefinite |  | 9
AR194108 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | UT | ***** | ***** | UT | ***** | ***** |  | AoA | Indefinite |  | 9
AR194196 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | UT | ***** | ***** | UT | ***** | ***** |  | AoA | Indefinite |  | 9
AR195014 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | KY | ***** | ***** | KY | ***** | ***** |  | AoA | Indefinite |  | 9
AR195015 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | KY | ***** | ***** | KY | ***** | ***** |  | AoA | Indefinite |  | 9
AR195458 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | NH | ***** | ***** | NH | ***** | ***** |  | AoA | Indefinite |  | 9
AR195461 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | NH | ***** | ***** | NH | ***** | ***** |  | AoA | Indefinite |  | 9
AR200153 | AN/TPQ-53 | ***** | 0 | ***** | 0 | Fixed Radar | ***** | KY | ***** | ***** | KY | ***** | ***** |  | AoA | Indefinite |  | 9

## Funds
System Name | Total Pre-Auction Cost ($M) | Funds Requested Prior to Auction ($M) | Pre-Auction Cost Pre-2012 ($M) | Transition Implementation Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months after Receipt of Funds) | End Expenditure Timeline (Months after Receipt of Funds) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
AN/TPQ-53 | 0 | 0 |  | 0 | 0
ARMY 3450-3: RPS-42 Interim Study | 0.94 | 0.94 |  | 0 | 0.94 | 1 | 30
ARMY-3450-1: Army & Commercial Industry Deployment Coordination | 3.82 | 3.82 |  | 14.77 | 18.59 | 1 | 78
ARMY-3450-2: AN/TPQ-53 Counter Fire Radar Study & Modification | 7.825 | 7.825 |  | 216.44 | 224.265 | 1 | 78
ARMY-3450-4: Electromagnetic Warfare (EW) PEO STRI | 1.02 | 1.02 |  | 0 | 1.02 | 1 | 30
Sequestration | 0 | 0 |  | 0 | 0
Total | 13.605 | 13.605 | 0 | 231.21 | 244.815 |  |  | 0

## Interactions
Interaction Name | Interaction Description
Development of Coordination Guidelines For Federal Agencies and Industry: | Given the fact that most federal operations will still be in the band upon the award of licenses by the FCC and some federal operations will continue indefinitely in the band, specific coordination guidelines must be developed and published by NTIA (for federal agencies) and the FCC (for non-federal licensees).

## Impact Factors
Factor Name | Factor Description
Incumbent Support | Incumbents will support interference testing to determine feasibility of co-existence and necessary equipment alterations, and they will support as necessary to address interference issues.
Transition Plan Includes Sensitive Information Not Releasable to the Public | In accordance with 47 USC 929 - National Security and Other Sensitive Information, the DoD CIO has determined that there is a legal basis for non-disclosure of certain information and that public disclosure of information designated CUI, taken in the aggregate as presented in this TP, would be detrimental to national security. Withholding the sensitive information has no impact on fulfillment of this transition plan as the protection areas and exclusion zones are already known to the public.

## Notes
Note Name | Note Text
3450-3550 MHz CPA and PUA | Cooperative Planning Areas (CPA): Geographic locations in which non-federal operations shall coordinate with federal systems in the band to deploy non-federal operations, in a manner that shall not cause harmful interference to federal systems operating in the band and to protect non-federal operations from potential harm caused by high powered federal operations. Periodic Use Areas (PUA): Geographic locations where non-federal operations in the band may not cause harmful interference to federal systems operating in the band for episodic periods. During such episodic time periods, non-federal users in PUAs must alter their operations to enable federal systems' temporary use of the band, and during such times, non-federal users may not claim interference protection from federal systems outside of coordination procedures.
5G Assumption | DoD was required to plan protection to and from 5G. An agreed standard was not available. Special subgroup that included the White House Office of Science and Technology (OSTP), DoD, the Federal Communications Commission (FCC), National Telecommunications and Information Administration (NTIA), and National Science Foundation (NSF) provided 5G assumptions for development of the initial plan. It was concluded that DoD would continue to work towards the topline goals in the Transition Plan by refining the assumptions with industry. (1) 5G Base Station Transmitter Power Output as Effective Isotropic Radiated Power (EIRP): (a) Urban: 1640 watts per megahertz (W/MHz); (b) Non-Urban: 3280 W/MHz (2) 5G Base Station Receiver Characteristics: Interference Power Input Density -35 dBm per meter squared (dBm/m2) or 0.01 Volts per meter (V/m) (3) Maximum Power Input: +35 dBm/m2 (4) 1 dB Compression (P1dB): -25 dBm for continuous wave signals referenced at antenna port (5) 20 MHz channels (6) Tower Height of 100 meters: Adjusted due to FCC requirement for an interference reporting declaration boundary
AMBIT Army 3450 MHz-1 | ARMY-3450-1: Army & Commercial Industry Deployment Coordination Objective(s): Provide management and oversight of Army Transition Plan Coordinate network laydown for 5G access for Industry while preserving critical DoD Readiness and Operations Ensure no loss to existing capability of developmental testing and large-scale training Achieved through bi-directional sharing agreement at 6 key installations System or Sites: Tobyhanna Army Depot, PA; Yuma Proving Grounds, AZ; WSMR, NM; Fort Sill, OK; National Training Center, CA; Joint Readiness Training Center, LA Readiness/Capability Impact: Inability to administrate sharing plans and effectively comply with federal business processes while supporting 5G requirements and protecting critical national security capabilities Benefits: Establishes bi-directional spectrum use at identified sites Ensures Army readiness and maintenance requirements
AMBIT Risks and Mitigation to DoD | In achieving the AMBIT Top Line goals, the DoD is accepting some risks and making assumptions that require further definition. The full operating electromagnetic environment is unknown and the definition of it is based on assumptions of 5G characteristics. The network laydowns are not yet available; as such, industry can be engaged to define a network laydown and engineering analysis to define CPAs and PUAs. The impact of ducting, particularly evaporation ducts for the Navy ships, are a known issue. An extensive detailed engineering analysis of the 5G environment and associated ducting can help address this issue. Out-of-band emissions are also a significant risk, in addition to unknown noise levels. Another definable problem includes a need for increased coordination between federal and non-federal entities for AMBIT to be successful. Spectrum compression due to increased number of systems in the lower band needs to be defined. In addition, DoD is incurring cost impacts as a result of increased testing, training, operational and acquisition timelines. This has a direct impact on critical electromagnetic warfare (EW) testing, training and exercise. Conducting analysis, research, and development and equipment modification or replacement to maintain comparable capability can help alleviate some of the unknowns. Potential solutions include but are not limited to: a. Backlobe/sidelobe suppression b. Sparse signal processing c. Receiver noise reduction As the network deploys, verification and validation of the electromagnetic environment can help provide a better picture of the new environment. Development of tools to reduce spectrum dependence from open-air testing and training as well as those to improve the efficiency of spectrum utilization can be utilized to mitigate some of the aforementioned issues. This in turn would assist in maintaining comparable capability and readiness in a shared spectrum environment. With adequate management, oversight and guidance of the transition, the overall transition plans will stand to see more viable success.
Army 3450 MHz-2 | ARMY-3450-2: AN/TPQ-53 Counter Fire Radar Study & Modification Objective(s): Conduct analysis of AN/TPQ-53 spectrum coexistence with overlapping operating frequencies 3450-3490 MHz Modify, test, and field AN/TPQ-53 hardware and software to maintain system agility and overall performance in a compressed and congested environment Systems or Sites: AN/TPQ-53 Readiness/Capability Impact: Decreased training rate by 20%, reduced number of radars from 5 to 4 employed simultaneously for training; further decreased when employed with AN/RPS-42 Interference from 5G networks to depot level radar far field testing Capability testing and large-scale training exercises limited to specific locations Benefit: Spectrum flexibility maintains large-scale training readiness, testing, and experimentation capabilities through compression, congestion, and spectrum sharing due to AMBIT 5G build-out
Army 3450 MHz-3 | ARMY-3450-3: Interim Maneuver Short Range Air Defense (IM-SHORAD) Study Objective(s): Conduct analysis of RPS-42 and AN/TPQ-53 spectrum coexistence interactions due to compression and congestion Investigate approaches to increase spectrum agility of RPS-42 to accommodate potential frequency expansion arrangements Investigate susceptibilities of RPS-42 to 5G emissions and 5G to RPS-42 emissions; identify appropriate mitigation strategies Systems: IM-SHORAD Sites: Tobyhanna Army Depot; PA; WSMR (primary test site), NM; Fort Sill, OK; National Training Center, CA; Joint Readiness Training Center, LA; Fort Bliss, TX; Fort Hood, TX; Joint Base Lewis McChord, WA; and Yakima Training Center, WA Readiness/Capability Impact: Reduced radar availability Increased maintenance timelines Reduced ranges for testing of new capabilities Benefit: Prevents losing large-scale training, testing, and experimentation capabilities due to compression, congestion, and coexistence when AN/TPQ-53 and RPS-42 operate in a significantly reduced shared frequency span. Study results will inform future IM-SHORAD tactics, techniques, and procedure development as well as informing technology insertions/upgrades
Army 3450 MHz-4 | ARMY-3450-4: Electromagnetic Warfare (EW) PEO STRI Objective(s): Conduct engineering analysis to identify the operational impact on the fleet of systems (communications, networks and range infrastructure/instrumentation) used by red/white cells during multi-domain operations due to the compressed operating environment resulting from spectrum sharing Define potential threat system modification and costs including design, range integration, testing, training, and retrofit System or Sites: Yuma Proving Grounds, AZ; WSMR, NM; Fort Huachuca Electronic Proving Grounds, AZ; Joint Base Lewis-McChord, WA; National Training Center, CA; and Joint Readiness Training Center, LA Readiness/Capability Impact: Reduced readiness and proficiency in protection ground forces operating in convoys, single vehicle operations, or fixed locations by blocking or jamming radio frequency (RF) signals intended to detonate improvised explosive devices (IEDs) Inability to provide Army Brigade Combat Team Commanders with an organic airborne offensive electromagnetic warfare (EW) capability Benefit: Maintain critical EW capabilities while providing 5G access
Checkpoints | It is recognized that a number of the identified solutions require further analysis and study. The final solutions will be compliant with allowable relocation or sharing costs and comparable capability of systems 47 USC 923(g)(3). Upon completion of each analysis and study effort, DOD will provide OMB with the results, and describe compliance with 47 USC 923(g)(3) so OMB can address its statutory oversight requirements. If requested, DOD will provide OMB status updates on analysis and study efforts via the SRF Resources Oversight Group (ROG). If required by OMB, Army will update its transition plan as specified in OMB's "Information for Eligible Federal Entities Related to Spectrum Transition Plan Updates (17-01)" to revise the cost estimate, funds expenditure timelines, or technical approach. No funds will be transferred until OMB has determined the appropriateness of the costs and the timeline for relocation or sharing in accordance with 47 USC 928(d)(2)(B).
Modification of Assignments | Upon conclusion of the transition, frequency assignments which authorize use in geographical areas that fall outside of CPAs and PUAs listed in US Footnote 431B will be modified to reflect operations shall not cause harmful interference to non-Federal operations in areas outside of the identified CPAs and PUAs.
Project Background: AMBIT Plan Top Line Goals | As agreed during the AMBIT effort, DoD will implement sharing via modifications to standard operating procedures (SOPs), tactics, techniques, and procedures (TTPs) or other operational-related means. Modifications to or replacement of some DoD equipment are required to restore comparable capability.
Timing of Funding Both Pre- and Post-Auction | DoD's timelines are based on the assumption that DoD will receive pre-auction funds no later than April 2021 and post auction funding in FY23Q1. If the auction date is accelerated, DoD assumes that post-auction funding will be received in FY22Q3. Additionally, DoD's costs and timelines assume that annual SRF disbursements will be received in Q1 of each FY. Should any receipt of funds be delayed, timelines and costs may need to be adjusted accordingly.

## Excluded Info
Table | Row | Column | CUI Category | Safeguarding and/or Dissemination Authority
Frequencies | AR100505 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR100505 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR100505 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR100505 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR100505 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR100505 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR100505 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111214 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111214 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111214 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111214 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111214 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111214 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111214 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111215 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111215 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111215 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111215 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111215 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111215 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111215 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111216 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111216 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111216 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111216 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111216 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111216 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR111216 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR130606 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR130606 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR130606 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR130606 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR130606 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR130606 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR130606 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135167 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135167 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135167 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135167 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135167 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135167 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135167 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135702 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135702 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135702 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135702 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135702 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135702 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR135702 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141406 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141406 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141406 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141406 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141406 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141406 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141406 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141412 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141412 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141412 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141412 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141412 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141412 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141412 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141683 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141683 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141683 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141683 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141683 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141683 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR141683 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145359 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145359 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145359 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145359 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145359 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145359 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145359 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145365 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145365 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145365 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145365 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145365 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145365 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145365 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145371 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145371 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145371 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145371 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145371 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145371 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145371 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145392 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145392 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145392 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145392 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145392 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145392 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR145392 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR151409 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR151409 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR151409 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR151409 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR151409 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR151409 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR151409 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR152600 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR152600 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR152600 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR152600 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR152600 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR152600 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR152600 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155115 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155115 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155115 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155115 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155115 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155115 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155115 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155432 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155432 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155432 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155432 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155432 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155432 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155432 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155433 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155433 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155433 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155433 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155433 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155433 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155433 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155434 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155434 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155434 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155434 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155434 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155434 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155434 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155438 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155438 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155438 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155438 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155438 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155438 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155438 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155439 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155439 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155439 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155439 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155439 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155439 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155439 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155440 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155440 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155440 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155440 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155440 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155440 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155440 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155445 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155445 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155445 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155445 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155445 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155445 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155445 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155446 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155446 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155446 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155446 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155446 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155446 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155446 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155450 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155450 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155450 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155450 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155450 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155450 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155450 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155451 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155451 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155451 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155451 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155451 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155451 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155451 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155452 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155452 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155452 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155452 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155452 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155452 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR155452 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR174079 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR174079 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR174079 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR174079 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR174079 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR174079 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR174079 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR184066 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR184066 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR184066 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR184066 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR184066 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR184066 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR184066 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192454 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192454 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192454 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192454 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192454 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192454 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192454 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192455 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192455 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192455 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192455 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192455 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192455 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192455 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192730 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192730 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192730 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192730 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192730 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192730 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR192730 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194107 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194107 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194107 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194107 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194107 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194107 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194107 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194108 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194108 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194108 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194108 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194108 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194108 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194108 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194196 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194196 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194196 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194196 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194196 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194196 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR194196 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195014 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195014 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195014 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195014 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195014 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195014 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195014 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195015 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195015 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195015 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195015 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195015 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195015 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195015 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195458 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195458 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195458 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195458 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195458 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195458 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195458 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195461 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195461 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195461 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195461 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195461 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195461 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR195461 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR200153 | Center Lower Frequency | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR200153 | Emission Bandwidth | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR200153 | Operation Area | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR200153 | Receiver Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR200153 | Receiver Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR200153 | Transmitter Latitude | DoD Critical Infrastructure Security Information | 10 USC 130e
Frequencies | AR200153 | Transmitter Longitude | DoD Critical Infrastructure Security Information | 10 USC 130e