## Title Page
Submitted: 8/28/2019
Approved: 10/4/2019
| First Name | Last Name | Office/Title | Phone Number | E-mail
Responsible Officer | Russell | Sveda | DOI, Office of the Chief Information Officer | 303-236-5091 | russell_sveda@ios.doi.gov
Alternate Contact | Carroll | Alexander | National Park Service | 202-354-1844 | carroll_alexander@nps.gov
Primary Contact | Russell | Sveda | DOI, Office of the Chief Information Officer | 303-236-5091 | russell_sveda@ios.doi.gov

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Alternate Frequency Assignment | Geographic Location associated with Timeline | Sharing Type | Indefinite Sharing Timeline (Months after 1/30/15) | Temporary Sharing Timeline (Months after 1/30/15) | Vacate Assignment Timeline (Months after 1/30/15)
I065234 | USPP/NPS | ***** |  | 6 | 5 | Video | ***** | DC | ***** | ***** | DC | ***** | ***** | N/A | DC | None |  |  | 24

## Funds
System Name | Total Pre-Auction Cost ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Cost Pre-2012 ($M) | Equipment Cost ($M) | Deployment Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months) | End Expenditure Timeline (Months) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
USPP/NPS | 0.15 | 0.15 | 0 | 6.581 | 2.215 | 8.946 | 6 | 60 | 0.53 | Point to Point Microwave Network, engineering, training and contract support to provide remote camera manipulation and receiver configuration control | Previously identified vulnerabilities in image transmission require non-dependant transmission of data/video. Point to point system negates this vulnerability. Remote camera manipulation and the ability to control receivers remotely enhance the effectiveness of the system and the need for more personnel on the aircraft. (See notes) Requesting 12 month extension until 9/2020. See Rev 3 under NOTES.
Total | 0.15 | 0.15 | 0 | 6.581 | 2.215 | 8.946 |  |  | 0.53

## Interactions
Interaction Name | Interaction Description
Sensitive information | While the specific frequency, system and location provided to the public, we have included a general location. We will share additional details with qualified bidders under a non-disclosure agreement. The redacted information will not impede fulfillment of the transition plan and should not have a significant impact on the auction since NPS will vacate in 24 months.

## Impact Factors
Factor Name | Factor Description
None anticipated.

## Notes
Note Name | Note Text
NPS Mission Information | *****
Rev1. Request for Extension of Expenditure of Funds Timeline | Request an extension for a total of 12 months bring the total number of months from 30 to 42 from 2/2018 to 3/2018 for expenditure of funds, the stakeholder has experience significant delays in spending that require third-party implementation and approvals which are beyond their control. The upgrades are done with new technology designs that require significant and elaborate engineering. In addition, these upgrades are being accomplished while maintaining stringent factory maintenance schedules and a continuous 24/7 mission operation in support of the National Capital Region.
Rev2. Request Extension of Expenditure of Fund Timeline | Need extension of timeline to complete the installation of the ground network that will support the mobile air system, requesting an additional six months bring the total number of months from 42 to 48 from 3/2019 to 9/2019.
Rev3. Request an Extension of Expenditure of Funds Timeline | NPS/USPP is requesting an extension for a total of 12 months bring the total number of months from 48 months to 60 months from 9/2019 to 10/2020 for the expenditure of funds. The stakeholders are in negotiation to secure a long-term operation and maintenance contract. The aviation communication upgrades were done with new technology designs that require significant and elaborate engineering support.

## Excluded Info
Table | Row | Column | Agency Marking | Reference
Frequencies | I065234 | Center Lower Frequency | Law Enforcement - Communications Sensitive (LES) | 47 U.S.C. § 929(a) and 18 U.S.C. § 2511
Frequencies | I065234 | Operation Area | Law Enforcement - Communications Sensitive (LES) | 47 U.S.C. § 929(a) and 18 U.S.C. § 2511
Frequencies | I065234 | Receiver Latitude | Law Enforcement - Communications Sensitive (LES) | 47 U.S.C. § 929(a) and 18 U.S.C. § 2511
Frequencies | I065234 | Receiver Longitude | Law Enforcement - Communications Sensitive (LES) | 47 U.S.C. § 929(a) and 18 U.S.C. § 2511
Frequencies | I065234 | Transmitter Latitude | Law Enforcement - Communications Sensitive (LES) | 47 U.S.C. § 929(a) and 18 U.S.C. § 2511
Frequencies | I065234 | Transmitter Longitude | Law Enforcement - Communications Sensitive (LES) | 47 U.S.C. § 929(a) and 18 U.S.C. § 2511
Notes | NPS Mission Information | Note Text | Law Enforcement-Communications Sensitive (LES) | 47 U.S.C. § 929(a) and 18 U.S.C. § 2511