## Title Page
Submitted: 7/8/2014
Approved: 1/6/2016
| First Name | Last Name | Office/Title | Phone Number | E-mail
Alternate Contact | Michael | Gilmore | FBI Next Generation Wireless Office | 202-439-0951 | michael.gilmore@ic.fbi.gov
Responsible Officer | Richard | Von Bostel | Law Enforcement Communications | 202-598-5794 | richard.a.vonbostel@usdoj.gov
Primary Contact | Richard | Von Bostel | Law Enforcement Communications | 202-598-5794 | richard.a.vonbostel@usdoj.gov

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Alternate Frequency Assignment | Geographic Location associated with Timeline | Sharing Type | Indefinite Sharing Timeline (Months after 1/30/15) | Temporary Sharing Timeline (Months after 1/30/15) | Vacate Assignment Timeline (Months after 1/30/15)
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Detroit Region | Coordinated |  | 29 | 41
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Northeast Region | Coordinated |  | 27 | 39
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | New Orleans Region | Coordinated |  | 28 | 40
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | California Region | Coordinated |  | 30 | 42
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Florida Region | Coordinated |  | 27 | 39
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | New York Region | Coordinated |  | 30 | 42
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | St. Louis Region | Coordinated |  | 29 | 41
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Washington DC Region | Coordinated |  | 27 | 39
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Chicago Region | Coordinated |  | 28 | 40
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Texas Region | Coordinated |  | 29 | 41
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Atlanta Region | Coordinated |  | 28 | 40
J032216 | Operational1 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Seattle Region | Coordinated |  | 30 | 42
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Washington DC Region | Coordinated |  | 27 | 39
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Seattle Region | Coordinated |  | 30 | 42
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Florida Region | Coordinated |  | 27 | 39
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New York Region | Coordinated |  | 30 | 42
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Northeast Region | Coordinated |  | 27 | 39
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New Orleans Region | Coordinated |  | 28 | 40
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Detroit Region | Coordinated |  | 29 | 41
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | California Region | Coordinated |  | 30 | 42
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | St. Louis Region | Coordinated |  | 29 | 41
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Chicago Region | Coordinated |  | 28 | 40
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Texas Region | Coordinated |  | 29 | 41
J039004 | Surveillance4 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Atlanta Region | Coordinated |  | 28 | 40
J042201 | Baltimore1 | ***** |  | ***** | 18 | Microwave | Microwave Link | DE | ***** | ***** | DE | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | DE-Baltimore | None |  |  | 30
J042229 | Washington DC | ***** |  | ***** | 18 | Microwave | Microwave Link | VA | ***** | ***** | VA | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | DC-Washington | None |  |  | 30
J042278 | San Diego | ***** |  | ***** | 18 | Microwave | Microwave Link | CA | ***** | ***** | CA | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | CA-San Diego | None |  |  | 30
J042307 | Minneapolis | ***** |  | ***** | 18 | Microwave | Microwave Link | MN | ***** | ***** | MN | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | MN-Minneapolis | None |  |  | 30
J042351 | New Orleans | ***** |  | ***** | 18 | Microwave | Microwave Link | LA | ***** | ***** | LA | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | LA-New Orleans | None |  |  | 30
J043969 | Houston | ***** |  | ***** | 18 | Microwave | Microwave Link | TX | ***** | ***** | TX | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | TX-Houston | None |  |  | 30
J052207 | Oklahoma City1 | ***** |  | ***** | 18 | Microwave | Microwave Link | OK | ***** | ***** | OK | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | OK-Oklahoma City | None |  |  | 30
J052208 | Oklahoma City2 | ***** |  | ***** | 18 | Microwave | Microwave Link | OK | ***** | ***** | OK | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | OK-Oklahoma City | None |  |  | 30
J052221 | Mobile | ***** |  | ***** | 18 | Microwave | Microwave Link | AL | ***** | ***** | AL | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | AL-Mobile | None |  |  | 30
J053257 | Birmingham | ***** |  | ***** | 18 | Microwave | Microwave Link | AL | ***** | ***** | AL | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | AL-Birmingham | None |  |  | 30
J053308 | Portland1 | ***** |  | ***** | 18 | Microwave | Microwave Link | OR | ***** | ***** | OR | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | OR-Portland | None |  |  | 30
J053700 | Knoxville | ***** |  | ***** | 18 | Microwave | Microwave Link | TN | ***** | ***** | TN | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | TN-Knoxville | None |  |  | 30
J053717 | Baltimore2 | ***** |  | ***** | 18 | Microwave | Microwave Link | MD | ***** | ***** | MD | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | MD-Baltimore | None |  |  | 30
J053791 | Dallas | ***** |  | ***** | 18 | Microwave | Microwave Link | TX | ***** | ***** | TX | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | TX-Dallas | None |  |  | 30
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Washington DC Region | Coordinated |  | 27 | 39
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New York Region | Coordinated |  | 30 | 42
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Atlanta Region | Coordinated |  | 28 | 40
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Texas Region | Coordinated |  | 29 | 41
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Detroit Region | Coordinated |  | 29 | 41
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Northeast Region | Coordinated |  | 27 | 39
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Chicago Region | Coordinated |  | 28 | 40
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | California Region | Coordinated |  | 30 | 42
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Florida Region | Coordinated |  | 27 | 39
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | St. Louis Region | Coordinated |  | 29 | 41
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Seattle Region | Coordinated |  | 30 | 42
J055907 | Surveillance2 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New Orleans Region | Coordinated |  | 28 | 40
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Atlanta Region | Coordinated |  | 28 | 40
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Chicago Region | Coordinated |  | 28 | 40
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | St. Louis Region | Coordinated |  | 29 | 41
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Florida Region | Coordinated |  | 27 | 39
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Detroit Region | Coordinated |  | 29 | 41
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Texas Region | Coordinated |  | 29 | 41
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New York Region | Coordinated |  | 30 | 42
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Seattle Region | Coordinated |  | 30 | 42
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Washington DC Region | Coordinated |  | 27 | 39
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New Orleans Region | Coordinated |  | 28 | 40
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | California Region | Coordinated |  | 30 | 42
J055908 | Surveillance3 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Northeast Region | Coordinated |  | 27 | 39
J062013 | Phoenix | ***** |  | ***** | 18 | Microwave | Microwave Link | AZ | ***** | ***** | AZ | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | AZ-Phoenix | None |  |  | 30
J062575 | Detroit | ***** |  | ***** | 18 | Microwave | Microwave Link | MI | ***** | ***** | MI | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | MI-Detroit | None |  |  | 30
J062594 | Portland2 | ***** |  | ***** | 18 | Microwave | Microwave Link | OR | ***** | ***** | OR | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | OR-Portland | None |  |  | 30
J062689 | Jacksonville | ***** |  | ***** | 18 | Microwave | Microwave Link | FL | ***** | ***** | FL | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | FL-Jacksonville | None |  |  | 30
J064554 | Buffalo | ***** |  | ***** | 18 | Microwave | Microwave Link | NY | ***** | ***** | NY | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | NY-Buffalo | None |  |  | 30
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Chicago Region | Coordinated |  | 28 | 40
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Washington DC Region | Coordinated |  | 27 | 39
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Seattle Region | Coordinated |  | 30 | 42
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New Orleans Region | Coordinated |  | 28 | 40
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Atlanta Region | Coordinated |  | 28 | 40
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Texas Region | Coordinated |  | 29 | 41
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Detroit Region | Coordinated |  | 29 | 41
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New York Region | Coordinated |  | 30 | 40
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | St. Louis Region | Coordinated |  | 29 | 41
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Florida Region | Coordinated |  | 27 | 39
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Northeast Region | Coordinated |  | 27 | 39
J071082 | Surveillance5 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | California Region | Coordinated |  | 30 | 42
J073001 | Miami | ***** |  | ***** | 18 | Microwave | Microwave Link | FL | ***** | ***** | FL | ***** | ***** | 4400-4940 MHz/8100-8500 MHz | FL-Miami | None |  |  | 30
J112600 | Operational7 | ***** |  | ***** | 8 | UAS | 80KM | VA | ***** | ***** | VA | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | VA | None |  |  | 30
J112602 | Operational5 | ***** |  | ***** | 8 | UAS | 80KM | TX | ***** | ***** | TX | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | TX | None |  |  | 30
J114544 | Operational3 | ***** |  | ***** | 8 | UAS | 80KM | CO | ***** | ***** | CO | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | CO | None |  |  | 30
J114546 | Operational4 | ***** |  | ***** | 8 | UAS | 80KM | TX | ***** | ***** | TX | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | TX | None |  |  | 30
J142505 | Operational6 | ***** |  | ***** | 8 | UAS | 80KM | VA | ***** | ***** | VA | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | VA | None |  |  | 30
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New York Region | Coordinated |  | 30 | 42
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Texas Region | Coordinated |  | 29 | 41
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | St. Louis Region | Coordinated |  | 29 | 41
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Detroit Region | Coordinated |  | 29 | 41
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Northeast Region | Coordinated |  | 27 | 39
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | California Region | Coordinated |  | 30 | 42
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Chicago Region | Coordinated |  | 28 | 40
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Seattle Region | Coordinated |  | 30 | 42
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Florida Region | Coordinated |  | 27 | 39
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New Orleans Region | Coordinated |  | 28 | 40
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Washington DC Region | Coordinated |  | 27 | 39
J904426 | Surveillance6 | ***** |  | ***** | 11 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Atlanta Region | Coordinated |  | 28 | 40
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Texas Region | Coordinated |  | 29 | 41
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Washington DC Region | Coordinated |  | 27 | 39
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Detroit Region | Coordinated |  | 29 | 41
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New Orleans Region | Coordinated |  | 28 | 40
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | California Region | Coordinated |  | 30 | 42
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Northeast Region | Coordinated |  | 27 | 39
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Atlanta Region | Coordinated |  | 28 | 40
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Seattle Region | Coordinated |  | 30 | 42
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | St. Louis Region | Coordinated |  | 29 | 41
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Florida Region | Coordinated |  | 27 | 39
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | Chicago Region | Coordinated |  | 28 | 40
J951326 | Surveillance1 | ***** |  | ***** | 18 | Video | USP | USP | ***** | ***** | USP | ***** | ***** | 1780-1850 MHz/2200-2290 MHz/4400-4940 MHz | New York Region | Coordinated |  | 30 | 42
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Chicago Region | Coordinated |  | 28 | 40
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Atlanta Region | Coordinated |  | 28 | 40
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Texas Region | Coordinated |  | 29 | 41
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Detroit Region | Coordinated |  | 29 | 41
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Florida Region | Coordinated |  | 27 | 39
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Northeast Region | Coordinated |  | 27 | 39
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | New Orleans Region | Coordinated |  | 28 | 40
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Washington DC Region | Coordinated |  | 27 | 39
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | California Region | Coordinated |  | 30 | 42
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | Seattle Region | Coordinated |  | 30 | 42
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | New York Region | Coordinated |  | 30 | 42
J991007 | Operational2 | ***** |  | ***** | 18 | Robotics | USP | USP | ***** | ***** | USP | ***** | ***** | 2200-2290 MHz/4400-4940 MHz | St. Louis Region | Coordinated |  | 29 | 41

## Funds
System Name | Total Pre-Auction Cost ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Cost Pre-2012 ($M) | Equipment Cost ($M) | Deployment Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months) | End Expenditure Timeline (Months) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
Baltimore1 | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Baltimore2 | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Birmingham | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Buffalo | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Dallas | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Detroit | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Houston | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Jacksonville | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Knoxville | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Miami | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Minneapolis | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Minnesota | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Mobile | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
New Orleans | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Oklahoma City1 | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Oklahoma City2 | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Operational1 | 0 | 0 | 0 | 3.96 | 0 | 3.96 | 3 | 30 |  |  | Relocation of Systems
Operational2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Relocation of Systems
Operational3 | 0 | 0 | 0 | 8.086 | 0 | 8.086 | 3 | 30 |  |  | Relocation of Systems
Operational4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Relocation of Systems
Operational5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Relocation of Systems
Operational6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Relocation of Systems
Operational7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Relocation of Systems
Phoenix | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Portland1 | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Portland2 | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
San Diego | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Surveillance1 | 2.221 | 2.221 | 0 | 462.429 | 106.247 | 570.897 | 3 | 96 | 15.95 | See Tab H 7 | Relocation of Systems
Surveillance2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Relocation of Systems
Surveillance3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Relocation of Systems
Surveillance4 | 0 | 0 | 0 | 179.316 | 53.021 | 232.337 | 3 | 96 | 3.05 | See Tab H 7 | Relocation of Systems
Surveillance5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Relocation of Systems
Surveillance6 | 0 | 0 | 0 | 252.295 | 33.755 | 286.05 | 3 | 96 | 3.98 | See Tab H 7 | Relocation of Systems
Washington DC | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 3 | 30 |  |  | Relocation of Systems
Total | 2.221 | 2.221 | 0 | 909.236 | 193.023 | 1104.48 |  |  | 22.98

## Interactions
Interaction Name | Interaction Description
1. Pre Auction Funds | It is assumed that Pre Auction Funds will be available in FY-14 for Pre Auction Planning of several key initiatives of the DOJ relocation strategy. Pre auction planning is crucial to the deployment timing of Adaptive Central Receive System and its associated components.
10. Adjustments To Base Budget | Reductions to the original DOJ Transition Plan were made at the request of the Technical Panel, including transitioning recurring costs beyond three years to annual Adjustments To Base Budget (ATB). This increases the risk for this transition plan because it now relies upon ATB during the deployment phase for success. At this time, this risk is rated as high.
11. DOJ Cost Reduction Risk | The Department of Justice’s (DOJ) revised transition plan includes an estimated total transition cost of $1.1 billion for planning and auction scoring purposes. This $1.1 billion estimate may increase or decrease based on continued review, including the results from a third-party cost review that will begin within the next few weeks. The execution of the funding may also shift during the transition implementation. The Department has worked closely with the Technical Panel to address questions and revise our transition plan based on Technical Panel direction, including changing the structure of recurring costs, eliminating a DOJ contingency reserve, and accepting a certain level of risk, particularly related to commercial service costs and potential price inflation. To reach the planning estimate of $1.1 billion, the Department has reduced its cost estimate by approximately $72 million in commercial services and $93 million in other areas from its most recent estimate of $1.265 billion. Overall, the Department has cut over $524 million from its initial transition estimate of $1.624 billion in order to meet the $1.1 billion planning estimate. The Department’s top priority is to ensure that law enforcement agencies do not lose surveillance capability after the AWS-III auction. This plan maintains comparable operational capability, but we are concerned that any further reductions, pending the third-party review, will compromise the ability of the Department to carry out its mission, including criminal investigations and national security matters. The Department will continue to review its cost estimates through the pending independent review and will revise the cost estimates based on the outcome of that review.
12. Temporary Sharing | For each of the frequency entries within Tab C that are labeled as "Vacate With Temp", the following stipulation applies: The concept of "temporary sharing" is subject to several conditions and these include: coordination requests will be addressed on a site-by-site basis and sharing conditions shall be approved by DOJ; sharing consideration will be assessed based on industry build-out/deployment plans and incumbent DOJ operations; and a recognition that industry be aware that sharing may be assessed as not feasible for an extended period of time. Industry should not assume that the label of "Vacate With Temp" indicates that sharing for that frequency is in any way assured. The label only means that DOJ is agreeable to determine if sharing is feasible in response to individual industry coordination requests. As noted in Tab D of this transition plan, in the "Begin Temoprary Sharing" column, DOJ will begin discussions and coordination of sharing 12 months prior to the "Vacate Assignment"dates listed in Tab D.
2. Sensitive Information that is not releasable to the public is included in the Transition Plan. | The redacted information will not impede fulfillment of the transition plan
3. Alternate Frequency Assignments | L Band = 1780-1850Mhz, C Band = 4400-4940Mhz, X Band = 8100-8500Mhz, S Band = 2200-2290Mhz
4. Tab D , Vacate Assignment Column | Dates are dependant on DOJ receipt of funds by May 2015
5. Tab E, Begin and End Expenditure of Funds Columns | Dates are dependant on DOJ receipt of funds by May 2015
6. Tab E, Expenditure of Funds beyond Vacate Spectrum Date | Funding is required beyond the Spectrum Vacate Date in order to build out the nationwide Adaptive Central Receive System and associated components
7. Tab E, Expanded Capability Costs | *****
8. Commercial Broadband Costs | The Commercial Broadband cost estimates are based on our ability to accurately estimate the future costs of broadband services. Existing contracts expire in 2014. At this time, this risk is rated as medium.
9. Vendor Costs and Schedule | The plan is dependant on vendors being able to meet DOJs estimated costs and schedules. At this time, this risk is rated as low.

## Impact Factors
Factor Name | Factor Description
1 | New frequency assignments in the GMF are required to be approved by NTIA by 12/31/2014 in the S and C Bands. This includes US&Ps throughout 2200 - 2290Mhz, 4400 - 4500 and 4600 - 4900 to include Band Assignments if required by NTIA.
2 | New frequency assignments in the GMF will be required to be approved by NTIA by 12/31/2014 in the L Band. This also includes assignments for a central receive control channel in each metropolitan area.
3 | New Point to Point frequency assignments in GMF will be required in 8100 - 8500Mhz.
4 | NTIA assistance with Commercial Carriers regarding their proposed dramatic increase in commercial services costs for Mobile Broadband is required.

## Notes
Note Name | Note Text
Atlanta Region | Atlanta, Charlotte, Columbia, Knoxville, Memphis, Nashville, Raleigh (EA 18, EA 19, EA 21, EA 22, EA 23, EA 24, EA 25, EA 26, EA 27, EA 28, EA 37, EA 38, EA 39, EA 40, EA 41, EA 42, EA 43, EA 44, EA 45, EA 46, EA 71, EA 73)
California Region | Honolulu, Las Vegas, Los Angeles, Sacramento, San Francisco, San Diego, Oakland (EA 151, EA 153, EA 160, EA 161, EA 162, EA 163, EA 164, EA 165, EA 172, EA 173, EA 175)
Chicago Region | Chicago, Indianapolis, Milwaukee, Minneapolis, Springfield, St Paul (EA 59, EA 63, EA 60, EA 66, EA 67, EA 68, EA 64, EA 65, EA 69, EA 97, EA 107, EA 109, EA 101, EA 102, EA 103, EA 104, EA 105, EA 106, EA 108, EA 110, EA 111, EA 112, EA 113)
Detroit Region | Cincinnati, Cleveland, Detroit, Louisville, Columbus (EA 47, EA 49, EA 50, EA 51, EA 55, EA 56, EA 57, EA 58, EA 61, EA 62, EA 70, EA 48, EA 52, EA 72)
Excluded Frequencies Information | (Added 10-14-2015) Law Enforcement Sensitive (LES) frequency and location information that was removed from the Frequencies Tab had to be replaced with "0s" in order to validate the Transition Plan.
Florida Region | Jacksonville, Miami, San Juan, Tampa, Orlando (EA 29, EA 30, EA 31, EA 32, EA 33, EA 34, EA 35, EA 81, EA 174, EA 176)
New Orleans Region | Birmingham, Jackson, Little Rock, Mobile, New Orleans (EA 36, EA 90, EA 76, EA 77, EA 82, EA 83, EA 84, EA 85, EA 86, EA 88, EA 89, EA 74, EA 75, EA 78, EA 79, EA 80, EA 91, EA 92, EA 95)
New York Region | Albany, Buffalo, New York (EA 5, EA 6, EA 7, EA 8, EA 10)
Northeast Region | Boston, New Haven, Newark, Philadelphia, Pittsburgh (EA 3, EA 12, EA 9, EA 11, EA 53, EA 54, EA 4, EA 1)
Regional Transition | DOJ's agencies are each organized and aligned differently with regard to geographic region. To assist with coordinating the transition out of this band, DOJ has coordinated the following common regions which have been aligned to Economic Areas, as identified by the CSMAC, for the transition timeline.
Seattle Region | Anchorage, Portland, Seattle (EA 2, EA 144, EA 145, EA 146, EA 147, EA 167, EA 168, EA 169, EA 170, EA 171, EA 166)
St Louis Region | Kansas City, Omaha, St. Louis, Denver, Salt Lake City (EA 96, EA 93, EA 94, EA 98, EA 99, EA 100, EA 114, EA 115, EA 116, EA 117, EA 119, EA 120, EA 121, EA 122, EA 123, EA 140, EA 141, EA 118, EA 148, EA 149, EA 152, EA 142, EA 143)
Texas Region | Oklahoma City, Dallas, Albuquerque, El Paso, Houston, San Antonio, Phoenix, Tucson, Austin (EA 87, EA 127, EA 128, EA 129, EA 130, EA 131, EA 132, EA 133, EA 134, EA 135, EA 136, EA 137, EA 138, EA 139, EA 124, EA 125, EA 126, EA 150, EA 154, EA 155, EA 156, EA 157, EA 158, EA 159)
Washington DC Region | Baltimore, Washington, Norfolk, Richmond (EA 13, EA 14, EA 15, EA 20, EA 16, EA 17)

## Excluded Info
Table | Row | Column | Agency Marking | Reference
Factors | 7. Tab E, Expanded Capability Costs | Factor Description | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J032216 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J032216 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J032216 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J032216 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J032216 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J032216 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J039004 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J039004 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J039004 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J039004 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J039004 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J039004 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042201 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042201 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042201 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042201 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042201 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042201 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042229 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042229 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042229 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042229 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042229 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042229 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042278 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042278 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042278 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042278 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042278 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042278 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042307 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042307 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042307 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042307 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042307 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042307 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042351 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042351 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042351 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042351 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042351 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J042351 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J043969 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J043969 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J043969 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J043969 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J043969 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J043969 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052207 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052207 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052207 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052207 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052207 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052207 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052208 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052208 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052208 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052208 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052208 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052208 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052221 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052221 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052221 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052221 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052221 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J052221 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053257 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053257 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053257 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053257 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053257 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053257 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053308 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053308 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053308 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053308 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053308 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053308 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053700 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053700 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053700 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053700 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053700 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053700 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053717 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053717 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053717 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053717 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053717 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053717 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053791 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053791 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053791 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053791 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053791 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J053791 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055907 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055907 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055907 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055907 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055907 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055907 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055908 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055908 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055908 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055908 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055908 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J055908 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062013 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062013 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062013 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062013 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062013 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062013 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062575 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062575 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062575 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062575 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062575 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062575 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062594 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062594 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062594 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062594 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062594 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062594 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062689 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062689 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062689 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062689 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062689 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J062689 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J064554 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J064554 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J064554 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J064554 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J064554 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J064554 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J071082 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J071082 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J071082 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J071082 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J071082 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J071082 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J073001 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J073001 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J073001 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J073001 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J073001 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J073001 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112600 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112600 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112600 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112600 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112600 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112600 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112602 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112602 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112602 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112602 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112602 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J112602 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114544 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114544 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114544 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114544 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114544 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114544 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114546 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114546 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114546 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114546 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114546 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J114546 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J142505 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J142505 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J142505 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J142505 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J142505 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J142505 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J904426 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J904426 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J904426 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J904426 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J904426 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J904426 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J951326 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J951326 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J951326 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J951326 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J951326 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J951326 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J991007 | Center Lower Frequency | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J991007 | Emission Bandwidth | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J991007 | Receiver Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J991007 | Receiver Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J991007 | Transmitter Latitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
Frequencies | J991007 | Transmitter Longitude | U//LES | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act