## A. Title Page (U)
Department of Defense Agency: Department of the Navy (DoN), US Navy and US Marine Corps Transition Plan for the 1755-1780 MHz Band
| Primary Point of Contact: Ms. Dru Pontius Office: Navy Marine Corps Spectrum Center Telephone Number: 301-225-3843 E-mail: dru.l.pontius@navy.mil |  | Alternate Point of Contact: Mr. Tom Downie Office: Director, Navy Marine Corps Spectrum Center Telephone Number: 301-225-3832 E-mail: tom.downie@navy.mil
Certification regarding Classified and Sensitive Information: I, [Name of Responsible Authority], certify that this transition plan, is cleared for release to the public and contains no classified or sensitive information. A separate version containing a complete transition plan including all sensitive data is provided under separate cover via authorized channels. ____________________________ Name: Thomas Kidd Title: Lead, Department of the Navy Strategic Spectrum Organization: Office of the Department of the Navy Chief Information Officer

## B. General Info (U)
1 | This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: |  | Yes
| a. Total pre-auction planning costs: | 4.1745 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer: | 4.1745
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012: | 1.9415
d. This organization attests that:
| [1] To the fullest extent possible, this transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] (Only applicable if the amount in 1b above is greater than $0.00.) Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | Yes
3 | There is additonal information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | Yes
4 | This Transition Plan includes both sensitive and unclassified information and comprises a full version of the Transition Plan for this agency. The only information that has been excluded are those elements that are classified. (Note: A version of this plan that contains only publicly releasable information is provided separately.) | No
5 | a. Name of Responsible Officer: | Ms. Dru Pontius
| b. (Optional) Office: | Navy Marine Corps Spectrum Center
| c. (Optional) Telephone Number: | 301-225-3843
| d. (Optional) E-mail: | dru.l.pontius@navy.mil
6 | Total Transition Plan Cost ($M): | 1396.9616

## C. Abstract (U)
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Releasable System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation (SEE TAB I) | Alternate Frequency Assignment | Transition Timeline (Months)
N 065621 | ***** |  | ***** | ***** | USN | UAS | ***** | DON UAS 1-4 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
N 065622 | ***** |  | ***** | ***** | USN | UAS | ***** | DON UAS 1-4 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
N 114003 | ***** |  | ***** | ***** | USN | UAS | ***** | DON UAS 3 | ***** | SC | ***** | ***** | SC | ***** | ***** | Vacate with temp | ***** | 48
N 138070 | ***** |  | ***** | ***** | USN | UAS | ***** | DON UAS 1-4 | ***** | OR | ***** | ***** | OR | ***** | ***** | Vacate with temp | ***** | 48
N 133790 | ***** |  | ***** | ***** | USN | UAS | ***** | DON UAS 3 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with temp | ***** | 48
MC 115319 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
MC 115335 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
MC 115336 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
MC 135302 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 4 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
MC 134519 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 4 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48 | Deleted, add replacement
MC 135216 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 4 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with temp | ***** | 48
MC 135224 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 4 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
MC 135225 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 4 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
MC 135303 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 4 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
MC 134520 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 4 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48 | Deleted, add replacement
MC 135217 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 4 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with temp | ***** | 48
MC 075673 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 085345 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 075692 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 87
N 075693 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 87
N 124502 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 1-5 | ***** | MD | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 87
N 124503 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 1-5 | ***** | MD | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 87
N 134566 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 1-5 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with temp | ***** | 51
N 134567 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 1-5 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with temp | ***** | 51
N 134580 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 1-5 | ***** | LANT | ***** | ***** | LANT | ***** | ***** | Vacate with temp | ***** | 51
N 134581 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 1-5 | ***** | LANT | ***** | ***** | LANT | ***** | ***** | Vacate with temp | ***** | 51
N 036003 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
N 036004 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
N 044843 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | MO | ***** | ***** | MO | ***** | ***** | Vacate with temp | ***** | 48
N 044844 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | MO | ***** | ***** | MO | ***** | ***** | Vacate with temp | ***** | 48
N 044880 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | MO | ***** | ***** | MO | ***** | ***** | Vacate with temp | ***** | 48
N 044881 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | MO | ***** | ***** | MO | ***** | ***** | Vacate with temp | ***** | 48
N 088081 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with temp | ***** | 48
N 088085 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with temp | ***** | 48
N 095421 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | SC | ***** | ***** | SC | ***** | ***** | Vacate with temp | ***** | 48
N 095427 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with temp | ***** | 48
N 099937 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | WA | ***** | ***** | WA | ***** | ***** | Vacate with temp | ***** | 48
N 099938 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | WA | ***** | ***** | WA | ***** | ***** | Vacate with temp | ***** | 48
N 947215 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with temp | ***** | 48
N 947225 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | SC | ***** | ***** | SC | ***** | ***** | Vacate with temp | ***** | 48
N 948077 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
N 948097 | ***** |  | ***** | ***** | USN | PGM | ***** | DoN PGM | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 48
N 797220 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018356 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018357 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018358 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018359 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018360 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018361 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018362 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018363 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018364 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018365 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 018366 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 028686 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028687 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028688 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028689 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028690 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028691 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028692 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028693 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028694 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028695 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028696 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028697 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028698 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028699 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028700 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028701 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028702 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028703 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028704 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028705 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028706 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028707 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 028708 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 88
N 028709 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 88
N 028710 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 036580 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 087939 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 087940 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 087941 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 087942 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 087943 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 88
N 136937 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136938 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136939 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136940 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136941 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136942 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136943 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136944 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136945 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136946 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136947 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136948 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136949 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 91
N 136950 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 91
N 136951 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136952 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136953 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136954 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136955 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136956 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 136957 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 085063 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085064 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085065 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085066 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 883073 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 063225 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 083981 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 63
N 085073 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085074 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085075 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085076 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085077 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085078 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 842898 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD Air | ***** | ***** | Vacate with Temp | ***** | 105
N 085079 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with Temp | ***** | 105
N 085080 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085081 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085082 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085083 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 085084 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD | ***** | ***** | Vacate with temp | ***** | 105
N 124403 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD Air | ***** | ***** | Vacate with temp | ***** | 12
N 063226 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | MD Air | ***** | ***** | MD Air | ***** | ***** | Vacate with temp | ***** | 105
N 876567 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Video 1 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 876579 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Video 1 | ***** | CA Air | ***** | ***** | CA | ***** | ***** | Vacate with temp | ***** | 91
N 876583 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Video 1 | ***** | NM Air | ***** | ***** | NM | ***** | ***** | Vacate with temp | ***** | 36
N 136919 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | NM Air | ***** | ***** | NM | ***** | ***** | Vacate with temp | ***** | 36
N 094061 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | FL | ***** | ***** | FL | ***** | ***** | Vacate with temp | ***** | 66
N 088457 | ***** |  | ***** | ***** | USN | UAS | ***** | FQM-151A | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 48
N 088612 | ***** |  | ***** | ***** | USN | UAS | ***** | L-3VNTXL-1A | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 126630 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 12
N 126631 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
N 126632 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | TX | ***** | ***** | TX | ***** | ***** | Vacate with Temp | ***** | 12
N 126633 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
N 126634 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
N 126635 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | TX | ***** | ***** | TX | ***** | ***** | Vacate with Temp | ***** | 12
N 126636 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | TX | ***** | ***** | TX | ***** | ***** | Vacate with Temp | ***** | 12
N 126637 | ***** |  | ***** | ***** | USN | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
N 988239 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 36
MC 121431 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 12
MC 121435 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 12
MC 121437 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 12
MC 121438 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 12
MC 121439 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 12
MC 121440 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | OH | ***** | ***** | OH | ***** | ***** | Vacate with Temp | ***** | 12
MC 121441 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | KY | ***** | ***** | KY | ***** | ***** | Vacate with Temp | ***** | 12
MC 121442 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | IN | ***** | ***** | IN | ***** | ***** | Vacate with Temp | ***** | 12
MC 121443 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | KY | ***** | ***** | KY | ***** | ***** | Vacate with Temp | ***** | 12
MC 121444 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | TN | ***** | ***** | TN | ***** | ***** | Vacate with Temp | ***** | 12
MC 121445 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 12
MC 121446 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 12
MC 121447 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | TN | ***** | ***** | TN | ***** | ***** | Vacate with Temp | ***** | 12
MC 121448 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | OH | ***** | ***** | OH | ***** | ***** | Vacate with Temp | ***** | 12
MC 121449 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | WV | ***** | ***** | WV | ***** | ***** | Vacate with Temp | ***** | 12
MC 124145 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
MC 124146 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12 | Deleted, submit replacement
MC 125155 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 12
MC 125312 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
MC 127802 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | LA | ***** | ***** | LA | ***** | ***** | Vacate with Temp | ***** | 12
MC 127903 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | NJ | ***** | ***** | NJ | ***** | ***** | Vacate with Temp | ***** | 12
MC 127906 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | GA | ***** | ***** | GA | ***** | ***** | Vacate with Temp | ***** | 12
MC 123104 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 12
N 045191 | ***** |  | ***** | ***** | DON | TRR | ***** | DoN TRR 1 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
N 045192 | ***** |  | ***** | ***** | DON | TRR | ***** | DoN TRR 1 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
N 050468 | ***** |  | ***** | ***** | DON | TRR | ***** | DoN TRR 1 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 60
N 050472 | ***** |  | ***** | ***** | DON | TRR | ***** | DoN TRR 1 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with Temp | ***** | 60
N 050473 | ***** |  | ***** | ***** | DON | TRR | ***** | DoN TRR 1 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with Temp | ***** | 60
N 050485 | ***** |  | ***** | ***** | DON | TRR | ***** | DoN TRR 1 | ***** | GLM | ***** | ***** | GLM | ***** | ***** | Vacate with Temp | ***** | 60
N 050506 | ***** |  | ***** | ***** | DON | TRR | ***** | DoN TRR 1 | ***** | GUM | ***** | ***** | GUM | ***** | ***** | Vacate with Temp | ***** | 60
N 050507 | ***** |  | ***** | ***** | DON | TRR | ***** | DoN TRR 1 | ***** | GUM | ***** | ***** | GUM | ***** | ***** | Vacate with Temp | ***** | 60
MC 086502 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 24
MC 087196 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 24 | Deleted, add replacement
MC 018450 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 018451 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 018452 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 018453 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60 | Deleted, add replacement
MC 018454 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60 | Deleted, add replacement
MC 107182 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | IN | ***** | ***** | IN | ***** | ***** | Vacate with Temp | ***** | 60
MC 107183 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | IN | ***** | ***** | IN | ***** | ***** | Vacate with Temp | ***** | 60
MC 107700 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | OH | ***** | ***** | OH | ***** | ***** | Vacate with Temp | ***** | 60
MC 062021 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 60
MC 062022 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 60
MC 077668 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 077669 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60 | Deleted, add replacement
MC 099553 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | IL | ***** | ***** | IL | ***** | ***** | Vacate with Temp | ***** | 60 | Deleted, add replacement
MC 030332 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 24 | Deleted, add replacement
MC 030333 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 24
MC 030334 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 24
MC 030335 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 24
MC 030336 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 24
MC 030337 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 24
MC 084001 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 24
MC 084002 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 24
MC 084003 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 24
MC 084004 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 24
MC 114529 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 24
MC 123004 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | GUM | ***** | ***** | GUM | ***** | ***** | Vacate with Temp | ***** | 60
MC 123005 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | GUM | ***** | ***** | GUM | ***** | ***** | Vacate with Temp | ***** | 60
MC 123006 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | GUM | ***** | ***** | GUM | ***** | ***** | Vacate with Temp | ***** | 60
MC 937173 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 60
MC 937174 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 60
MC 937175 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 60
MC 937176 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 60
MC 955043 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 955044 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 955045 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 955046 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 955047 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 955048 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 955049 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 957106 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | NY | ***** | ***** | NY | ***** | ***** | Vacate with Temp | ***** | 60
MC 998023 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 929345 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 24
MC 929346 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 24
MC 937224 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with Temp | ***** | 24
N 055564 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 067148 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 075700 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 114281 | ***** |  | ***** | ***** | USMC | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 134587 | ***** |  | ***** | ***** | USMC | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 126558 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 126559 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127980 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127981 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127984 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127985 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127988 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127989 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127992 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127993 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127996 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 127997 | ***** |  | ***** | ***** | USN | ROBOTICS | ***** | DoN Robotics | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
N 957125 | ***** |  | ***** | ***** | NAVY | TT&C | ***** | DoN TT&C SatOps | ***** | MD | ***** | ***** | SPC | ***** | ***** | Indefinite | ***** | 12
N 957126 | ***** |  | ***** | ***** | NAVY | TT&C | ***** | DoN TT&C SatOps | ***** | MD | ***** | ***** | SPC | ***** | ***** | Indefinite | ***** | 12
N 957127 | ***** |  | ***** | ***** | NAVY | TT&C | ***** | DoN TT&C SatOps | ***** | MD | ***** | ***** | SPC | ***** | ***** | Indefinite | ***** | 12
N 957128 | ***** |  | ***** | ***** | NAVY | TT&C | ***** | DoN TT&C SatOps | ***** | MD | ***** | ***** | SPC | ***** | ***** | Indefinite | ***** | 12
N 957129 | ***** |  | ***** | ***** | NAVY | TT&C | ***** | DoN TT&C SatOps | ***** | MD | ***** | ***** | SPC | ***** | ***** | Indefinite | ***** | 12
N 113380 | ***** |  | ***** | ***** | Navy | TT&C | ***** | DoN TT&C SatOps | ***** | MD | ***** | ***** | SPC | ***** | ***** | Indefinite | ***** | 12
N 087583 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 63
N 087585 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 63
N 087587 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 63
N 087589 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 63
N 087591 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 63
N 087593 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 63
N 087595 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 63
N 087597 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 63
N 087599 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 63
N 087601 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 63
N 087603 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 63
N 085147 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | SC | ***** | ***** | SC | ***** | ***** | Vacate with Temp | ***** | 63
N 085148 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | SC | ***** | ***** | SC | ***** | ***** | Vacate with Temp | ***** | 63
N 085149 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | GA | ***** | ***** | GA | ***** | ***** | Vacate with Temp | ***** | 63
N 085150 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | SC | ***** | ***** | SC | ***** | ***** | Vacate with Temp | ***** | 63
N 124779 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | FL | ***** | ***** | FL | ***** | ***** | Vacate with Temp | ***** | 63
N 087559 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087560 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087561 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087562 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087563 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087564 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087565 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087566 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087567 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087568 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087569 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 087570 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 63
N 136637 | ***** |  | ***** | ***** | USN | ACTS | ***** | DoN ACTS | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 63
N 053455 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | LANT | ***** | ***** | LANT | ***** | ***** | Vacate with Temp | ***** | 12
N 053456 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | LANT | ***** | ***** | LANT | ***** | ***** | Vacate with Temp | ***** | 12
N 053457 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | LANT | ***** | ***** | LANT | ***** | ***** | Vacate with Temp | ***** | 12
N 053464 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | GLM | ***** | ***** | GLM | ***** | ***** | Vacate with Temp | ***** | 12
N 053465 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | GLM | ***** | ***** | GLM | ***** | ***** | Vacate with Temp | ***** | 12
N 053466 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | GLM | ***** | ***** | GLM | ***** | ***** | Vacate with Temp | ***** | 12
N 088694 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
N 094519 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 12
N 103501 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with Temp | ***** | 12
N 103502 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with Temp | ***** | 12
N 103503 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with Temp | ***** | 12
N 125870 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 12
N 137579 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
N 967058 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | NJ | ***** | ***** | NJ | ***** | ***** | Vacate with Temp | ***** | 48
N 128025 | ***** | ***** | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | MO | ***** | ***** | MO | ***** | ***** | Vacate with Temp | ***** | 36
N 018190 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 36
N 018202 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 36
N 135186 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | HI | ***** | ***** | HI | ***** | ***** | Vacate with Temp | ***** | 12
N 088211 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 60
N 088212 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 60
N 088213 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 60
N 088214 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 60
N 088215 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 60
N 088216 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 60
N 088217 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 60
N 088218 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 8 | ***** | NV | ***** | ***** | NV | ***** | ***** | Vacate with Temp | ***** | 60
N 851350 | ***** |  | ***** | ***** | USN | Telemetry | ***** | DoN Telemetry 1-5 | ***** | FL | ***** | ***** | FL | ***** | ***** | Vacate with Temp | ***** | 66
MC 126002 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 48
MC 130025 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 48
MC 124401 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 124518 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 124545 | ***** |  | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 134339 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
MC 134338 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Telemetry 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
MC 042001 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | NC | ***** | ***** | NC | ***** | ***** | Vacate with Temp | ***** | 24
MC 998024 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60 | Deleted, add replacement
MC 998025 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 24
MC 998026 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 24
MC 998027 | ***** |  | ***** | ***** | USMC | TRR | ***** | DoN TRR 2 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 60
MC 139346 | ***** |  | ***** | ***** | USMC | ROBOTICS | ***** | DoN Robotics | ***** | VA | ***** | ***** | VA | ***** | ***** | Vacate with Temp | ***** | 48
MC 125105 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Other 1-5 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 51
MC 125106 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Other 1-5 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 51
MC 135317 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Other 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 51
MC 135318 | ***** |  | ***** | ***** | USMC | Video | ***** | DoN Other 1-5 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 51 | Deleted, replacement frequency to be assigned
N 010206 | ***** |  | ***** | ***** | Navy | TT&C | ***** | DoN TT&C SatOps | ***** | ME | ***** | ***** | SPC | ***** | ***** | Indefinite | ***** | 12
N 010209 | ***** |  | ***** | ***** | Navy | TT&C | ***** | DoN TT&C SatOps | ***** | GUM | ***** | ***** | SPC | ***** | ***** | Indefinite | ***** | 12
N 127860 | ***** |  | ***** | ***** | USN | Other | ***** | DoN Other 7 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 12
MC 134639 | ***** | ***** | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 134739 | ***** | ***** | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 134778 | ***** | ***** | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 135113 | ***** | ***** | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | CA | ***** | ***** | CA | ***** | ***** | Vacate with Temp | ***** | 48
MC 135119 | ***** | ***** | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 48
MC 135124 | ***** | ***** | ***** | ***** | USMC | UAS | ***** | DON UAS 3 | ***** | AZ | ***** | ***** | AZ | ***** | ***** | Vacate with Temp | ***** | 48

## D. Transition Timeline(U)
Timeline (Months after Transition Start)
Serial Number | Geographic Location | Temporary Sharing | Indefinite Sharing | Vacate Assignment
N 065621 |  | 12
N 065622 |  | 12
N 114003 |  | 12
N 138070 |  | 12
MC 115319 |  | 12
MC 115335 |  | 12
MC 115336 |  | 12
MC 135302 |  | 12
MC 134519 |  | 12
MC 135216 |  | 12
MC 135224 |  | 12
MC 135225 |  | 12
MC 135303 |  | 12
MC 134520 |  | 12
MC 135217 |  | 12
MC 075673 |  | 12
MC 085345 |  | 12
N 075692 |  | 12
N 075693 |  | 12
N 124502 |  | 12
N 124503 |  | 12
N 134566 |  | 12
N 134567 |  | 12
N 134580 |  | 12
N 134581 |  | 12
N 036003 |  | 12
N 036004 |  | 12
N 044843 |  | 12
N 044844 |  | 12
N 044880 |  | 12
N 044881 |  | 12
N 088081 |  | 12
N 088085 |  | 12
N 095421 |  | 12
N 095427 |  | 12
N 099937 |  | 12
N 099938 |  | 12
N 947215 |  | 12
N 947225 |  | 12
N 948077 |  | 12
N 948097 |  | 12
N 797220 |  | 12
N 876567 |  | 12
N 018190 |  | 12
N 018202 |  | 12
N 018356 |  | 12
N 018357 |  | 12
N 018358 |  | 12
N 018359 |  | 12
N 018360 |  | 12
N 018361 |  | 12
N 018362 |  | 12
N 018363 |  | 12
N 018364 |  | 12
N 018365 |  | 12
N 018366 |  | 12
N 028686 |  | 12
N 028687 |  | 12
N 028688 |  | 12
N 028689 |  | 12
N 028690 |  | 12
N 028691 |  | 12
N 028692 |  | 12
N 028693 |  | 12
N 028694 |  | 12
N 028695 |  | 12
N 028696 |  | 12
N 028697 |  | 12
N 028698 |  | 12
N 028699 |  | 12
N 028700 |  | 12
N 028701 |  | 12
N 028702 |  | 12
N 028703 |  | 12
N 028704 |  | 12
N 028705 |  | 12
N 028706 |  | 12
N 028707 |  | 12
N 028708 |  | 12
N 028709 |  | 12
N 028710 |  | 12
N 036580 |  | 12
N 087939 |  | 12
N 087940 |  | 12
N 087941 |  | 12
N 087942 |  | 12
N 087943 |  | 12
N 136937 |  | 12
N 136938 |  | 12
N 136939 |  | 12
N 136940 |  | 12
N 136941 |  | 12
N 136942 |  | 12
N 136943 |  | 12
N 136944 |  | 12
N 136945 |  | 12
N 136946 |  | 12
N 136947 |  | 12
N 136948 |  | 12
N 136949 |  | 12
N 136950 |  | 12
N 136951 |  | 12
N 136952 |  | 12
N 136953 |  | 12
N 136954 |  | 12
N 136955 |  | 12
N 136956 |  | 12
N 136957 |  | 12
N 085063 |  | 12
N 085064 |  | 12
N 085065 |  | 12
N 085066 |  | 12
N 883073 |  | 12
N 063225 |  | 12
N 085073 |  | 12
N 085074 |  | 12
N 085075 |  | 12
N 085076 |  | 12
N 085077 |  | 12
N 085078 |  | 12
N 842898 |  | 12
N 085079 |  | 12
N 085080 |  | 12
N 085081 |  | 12
N 085082 |  | 12
N 085083 |  | 12
N 124403 |  | 12
N 063226 |  | 12
N 085084 |  | 12
N 876567 |  | 12
N 876579 |  | 12
N 876583 |  | 12
N 136919 |  | 12
N 094061 |  | 12
N 088457 |  | 12
N 088612 |  | 12
N 988239 |  | 12
N 045191 |  | 12
N 045192 |  | 12
N 050468 |  | 12
N 050472 |  | 12
N 050473 |  | 12
N 050485 |  | 12
N 050506 |  | 12
N 050507 |  | 12
MC 086502 |  | 12
MC 087196 |  | 12
MC 018450 |  | 12
MC 018451 |  | 12
MC 018452 |  | 12
MC 018453 |  | 12
MC 018454 |  | 12
MC 107182 |  | 12
MC 107183 |  | 12
MC 107700 |  | 12
MC 062021 |  | 12
MC 062022 |  | 12
MC 077668 |  | 12
MC 077669 |  | 12
MC 099553 |  | 12
MC 030332 |  | 12
MC 030333 |  | 12
MC 030334 |  | 12
MC 030335 |  | 12
MC 030336 |  | 12
MC 030337 |  | 12
MC 084001 |  | 12
MC 084002 |  | 12
MC 084003 |  | 12
MC 084004 |  | 12
MC 114529 |  | 12
MC 123004 |  | 12
MC 123005 |  | 12
MC 123006 |  | 12
MC 937173 |  | 12
MC 937174 |  | 12
MC 937175 |  | 12
MC 937176 |  | 12
MC 955043 |  | 12
MC 955044 |  | 12
MC 955045 |  | 12
MC 955046 |  | 12
MC 955047 |  | 12
MC 955048 |  | 12
MC 955049 |  | 12
MC 957106 |  | 12
MC 998023 |  | 12
MC 929345 |  | 12
MC 929346 |  | 12
MC 937224 |  | 12
MC 042001 |  | 12
N 055564 |  | 12
N 067148 |  | 12
N 075700 |  | 12
MC 114281 |  | 12
MC 134587 |  | 12
N 126558 |  | 12
N 126559 |  | 12
N 127980 |  | 12
N 127981 |  | 12
N 127984 |  | 12
N 127985 |  | 12
N 127988 |  | 12
N 127989 |  | 12
N 127992 |  | 12
N 127993 |  | 12
N 127996 |  | 12
N 127997 |  | 12
N 087583 |  | 12
N 087585 |  | 12
N 087587 |  | 12
N 087589 |  | 12
N 087591 |  | 12
N 087593 |  | 12
N 087595 |  | 12
N 087597 |  | 12
N 087599 |  | 12
N 087601 |  | 12
N 087603 |  | 12
N 085147 |  | 12
N 085148 |  | 12
N 085149 |  | 12
N 085150 |  | 12
N 124779 |  | 12
N 083981 |  | 12
N 087559 |  | 12
N 087560 |  | 12
N 087561 |  | 12
N 087562 |  | 12
N 087563 |  | 12
N 087564 |  | 12
N 087565 |  | 12
N 087566 |  | 12
N 087567 |  | 12
N 087568 |  | 12
N 087569 |  | 12
N 087570 |  | 12
N 136637 |  | 12
N 967058 |  | 12
N 128025 |  | 12
N 088211 |  | 12
N 088212 |  | 12
N 088213 |  | 12
N 088214 |  | 12
N 088215 |  | 12
N 088216 |  | 12
N 088217 |  | 12
N 088218 |  | 12
N 851350 |  | 12
MC 126002 |  | 12
MC 130025 |  | 12
MC 124401 |  | 12
MC 124518 |  | 12
MC 124545 |  | 12
MC 998024 |  | 12
MC 998025 |  | 12
MC 998026 |  | 12
MC 998027 |  | 12
MC 139346 |  | 12
MC 125105 |  | 12
MC 125106 |  | 12
MC 135317 |  | 12
MC 135318 |  | 12
MC 134639 |  | 12
MC 134739 |  | 12
MC 134778 |  | 12
MC 135113 |  | 12
MC 135119 |  | 12
MC 135124 |  | 12

## E. Timeline for Funds (U)
System Name | Releasable System Name | System ID | Releasable System ID | Total Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
***** | DON UAS 1 | ***** | DON-1 | 0.068845 | 0.068845 | 0.068845 | 6.332 | 0 | 6.4009 | 1 | 17
***** | DON UAS 2 | ***** | DON-2 | 0.068845 | 0.068845 | 0.068845 | 33.2502 | 0 | 33.3191 | 1 | 53
***** | DON UAS 3 | ***** | DON-3 | 0.068845 | 0.068845 | 0.068845 | 31.3336 | 0 | 31.4024 | 1 | 41
***** | DON UAS 4 | ***** | DON-4 | 0.068845 | 0.068845 | 0.068845 | 33.3201 | 0 | 33.389 | 1 | 74
***** | DON UAS Transition Support | ***** | DON-5 | 0 | 0 | 0 | 3.7 | 12.985 | 16.685 | 1 | 120 |  |  | Includes direct participation by Program office in sharing studies, development and administering of training relative to spectrum transition impacts on capability, configuration management of capability and support systems, and development, validation and briefing of material required for SRF progress reporting
*****
***** | DoN UAS-Video 5 | ***** | DON-6 | 0 | 0 | 0 | 94.2 | 0 | 94.2 | 4 | 120
*****
***** | DoN Video Transition Support | ***** | DON-8 | 0 | 0 | 0 | 3.7 | 12.985 | 16.685 | 1 | 120 |  |  | Includes direct participation by Program office in sharing studies, development and administering of training relative to spectrum transition impacts on capability, configuration management of capability and support systems, and development, validation and briefing of material required for SRF progress reporting
*****
***** | DoN Other 1 | ***** | DON-9 | 0.001 | 0.001 | 0.001 | 174.035 |  | 174.036 | 1 | 87
***** | DoN Other 2 | ***** | DON-10 | 0.001 | 0.001 | 0.001 | 53.0022 |  | 53.0032 | 1 | 87
***** | DoN Other 3 | ***** | DON-11 | 0.001 | 0.001 | 0.001 | 161.3656 |  | 161.3666 | 1 | 120
***** | DoN Other 4 | ***** | DON-12 | 0.001 | 0.001 | 0.001 | 151.5844 |  | 151.5854 | 1 | 120
***** | DoN Other 5 | ***** | DON-13 | 0.001 | 0.001 | 0.001 | 79.9398 |  | 79.9408 | 1 | 120
***** | DoN Other Systems Transition Support | ***** | DON-14 | 0 | 0 | 0 | 3.7 | 12.985 | 16.685 | 1 | 120 |  |  | Includes direct participation by Program office in sharing studies, development and administering of training relative to spectrum transition impacts on capability, configuration management of capability and support systems, and development, validation and briefing of material required for SRF progress reporting
*****
***** | DoN PGM | ***** | DON-15 | 0.105 | 0.105 | 0.105 | 24.387 |  | 24.492 | 1 | 120
***** | DoN PGM Transition Support | ***** | DON-16 | 0 | 0 | 0 | 3.7 | 12.985 | 16.685 | 1 | 120 |  |  | Includes direct participation by Program office in sharing studies, development and administering of training relative to spectrum transition impacts on capability, configuration management of capability and support systems, and development, validation and briefing of material required for SRF progress reporting
*****
***** | DoN Telemetry 1 | ***** | DON-17 | 0.088161 | 0.088161 | 0.088161 | 25.5787 | 5.1905 | 30.8574 | 1 | 120 | 0 | NA | *****
***** | DoN Telemetry 2 | ***** | DON-18 | 0.088161 | 0.088161 | 0.088161 | 23.7852 | 3.4245 | 27.2978 | 1 | 120 | 0 | NA | *****
***** | DON Telemetry 3 | ***** | DON-19 | 0 | 0 | 0 | 4.4296 | 0.45694 | 4.8865 | 1 | 120 | 0 | NA | Re-engineering of AMT systems and capabilities, and to purchase new equipment to allow the systems to compress into the 1780 - 1850 MHz portion of the band. Also see note below and TAB I for additional information.
***** | DoN Telemetry 4 | ***** | DON-20 | 0.088161 | 0.088161 | 0.088161 | 34.2247 | 6.9877 | 41.3006 | 1 | 120 | 0 | NA | *****
***** | DoN Telemetry 5 | ***** | DON-21 | 0 | 0 | 0 | 1.069 | 0.21575 | 1.2847 | 1 | 36 | 0 | NA | Re-engineering of AMT systems and capabilities, and to purchase new equipment to allow the systems to compress into the 1780 - 1850 MHz portion of the band. Also see note below and TAB I (Note 4) for additional information.
***** | DoN Video 1 | ***** | DON-7 | 0 | 0 | 0 | 1.091 | 0.452 | 1.543 | 1 | 36 | 0 | NA | Re-engineering of AMT systems and capabilities, and to purchase new equipment to allow the systems to compress into the 1780 - 1850 MHz portion of the band. Also see note below and TAB I (Note 4) for additional information.
***** | [8 empty] | 0
***** | DoN TRR 1 | ***** | DON-22 | 0 | 0 | 0.132 | 126.8 | 0 | 126.8 | 1 | 120 | 0 | NA | *****
***** | DoN TRR 2 | ***** | DON-23 | 0 | 0 | 0 | 5.3 | 0 | 5.3 | 1 | 120 | 0 | NA | *****
***** | DoN TRR 3 | ***** | DON-24 | 0 | 0 | 0 | 6.4705 | 18.998 | 25.4685 | 1 | 120 |  |  | Includes direct participation by Program office in sharing studies, development and administering of training relative to spectrum transition impacts on capability, configuration management of capability and support systems, and development, validation and briefing of material required for SRF progress reporting
***** | [8 empty] | 0
***** | DoN Robotics | ***** | DON-25 | 0.05821 | 0.058209 | 0.058209 | 85.0412 | 25.9588 | 111.0582 | 1 | 52 | 0 | N/A | *****
| DoN Robotics Transition Support | ***** | DON-26 | 0 | 0 | 0 | 3.7 | 12.985 | 16.685 | 1 | 120 | 0 |  | Includes direct participation by Program office in sharing studies, development and administering of training relative to spectrum transition impacts on capability, configuration management of capability and support systems, and development, validation and briefing of material required for SRF progress reporting
***** | DoN TT&C SatOps |  | DON-27 | 0.086092 | 0.086092 | 0.086092 | 0 | 0.896 | 0.98209 | 1 | 120 | N/A |  | a)Pre Auction cost are for man-hours and costs incurred associated with research, engineering studies, analyses, travel, meetings and discussions and filing presentations and reports in connection with the sharing or relocations plan. BPTF is industrial funded and therefore has no budget for this task. b) Deployment related costs are to cover time costs incurred for managing and supporting the sharing plan with AWS for 10 years
***** | DoN ACTS | ***** | DON-28 | 0 | 0 | 0 | 0 | 12.359 | 12.359 | 1 | 60 | NONE | N/A | N/A
***** | DoN HQ Transition Process Management | ***** | DON-29 | 3.3803 | 3.3803 | 1.0153 | 6.071 | 71.812 | 81.2633 | 1 | 120 |  |  | Establish coordination processes and contract vehicles in preparation for post-auction coordination activities, process spectrum certification requests, mangage allocation of transition assignments, monitor use of new compressed spectrum, monitor and report encroachment, monitor and resolve interference, lead and coordinate spectrum sharing studies,develop support/service contract, allocate, oversee and monitor expenditures and coordinate SRF reports
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## F. NTIA Interactions
Interaction required with NTIA to implement this Transition Plan
1 | Spectrum Certification: This Transition Plan is based on the DoD Alternative Proposal for the 1755-1780 MHz band; details can be found in Tab I (Additional Information). As part of the Transition Plan, some systems will be modified to operate in both the 1780-1850 MHz and the 2025-2110 MHz bands, while other systems will be retuned or modified to operate in other federal bands. All modified equipment will be required to undergo the spectrum certification process through the NTIA Spectrum Planning Subcommittee (SPS) IAW OMB Circular A-11, Section 31.12(c). This certification is required before agencies can "submit estimates for the development or procurement of major radio spectrum-dependent communications-electronics systems". The spectrum certification process through the NTIA Spectrum Planning Subcommittee can require a number of months to complete for routine equipment developments. It is anticipated that due to the numerous simultaneous certification requests required to enable the modification and/or replacement of the systems identified in this and other agencies' Transition Plans, there will be a significant backlog within the SPS process. It should also be noted that the spectrum certification process is required at each stage of a program's development and thus some of the modified or relocated systems systems may be required to undergo the SPS review process multiple times. These interactions will begin soon after this Transition Plan is approved and will continue until all affected systems receive spectrum certification approval from the SPS.
2 | Frequency Authorization: All systems that require either different frequency assignments in the 1780-1850 MHz band, modification to operate in both the 1780-1850 MHz and 2025-2110 MHz frequency bands, or relocation to operate in other federal bands will have to follow the frequency authorization process in order to obtain new frequency authorizations. It is understood that NTIA intends to essentially "reserve" frequency assignments in the alternate spectrum bands based on the data provided in this Transition Plan; however, the formal frequency authorization process through the NTIA Frequency Assignment Subcommittee (FAS) must still be completed at a future time, subsequent to the associated SPS certification process for the systems/equipments and prior to actual operations in the alternate bands and verification/validation of comparable technical capability. These interactions will begin soon after this Transition Plan is approved and will continue until all affected systems become operational in dual or alternate frequency bands as defined by the Transition Plan.
3 | Federal Communications Commission (FCC) band allocation rules development and adoption. The allocation for and use of this band by non-federal fixed and mobile users will require the development of specific technical rules governing non-federal operations, such that sharing of the band between federal and non-federal users is feasible and jointly successful. The development of these rules will be critical to the successful implementation of the DoD Alternative Proposal and the associated transition of systems addressed in this plan from the band. These rules must be adopted prior to the auction of the 1755-1780 MHz band such that potential licensees are fully aware of the requirements that they must comply with to begin operations in the band.
4 | Development of Coordination Guidelines For Federal Agencies and Industry: Given the fact that most federal operations will still be in the band upon the award of licenses by the FCC and some federal operations will continue indefinitely in the band, specific coordination guidelines must be developed and published by NTIA (for federal agencies) and the FCC (for non-federal licensees). The formal development of these coordination procedures has not yet begun by NTIA and the FCC, but they will be essential to the any early entry by licensees as well as for the long term sharing coordination that will be required.
5 | None, assuming that new 1494s will be processed under the normal timeline and through the normal process.
6 | *****
7 | NTIA and the FCC to adopt specific Regulatory Criteria required to protect the out of Band Emissions (OOBE) by the Wireless Industry UEs and base stations to the AMT receiver sites. This OOBE protection is requested through the AWS-3 NPRM with the FCC and will include the defined requirements for DoD's AMT Standards for protection via ITU-R-M.1459.
8 | DOJ systems will be required to migrate to digital modulations to reduce system bandwidth to allow AMT efficient modulation systems to share the band where applicable. All use by DOJ in this band must be accurately documented in the GMF so the DoD may de-conflict through engineering analysis.
9 | *****

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference
For All serial numbers (frequency assignments from Tab C) except those listed below. | The sensitive information withheld includes the Center Frequency/Lower Band Limit, Upper Band Limit, Emission Bandwidth, RX IF Bandwidth, Non-Releasable System Name, Authorized Area of Operation, Transmit Latitude and Longitude, Receiver Latitude and Longitude, and Alternate Frequency Assignment. This information is currently designated as FOR OFFICIAL USE ONLY and is considered to have a legal basis for nondisclosure and public disclosure of this information would be detrimental to national security. Note: DoD policy and procedures for marking, use, and protection of FOUO information is in the process of migrating to the Controlled Unclassified Information (CUI) program provided under EO 13556. As this time, specific DoD CUI categories are in the process of being registered and will eventually serve as the basis for protection of this type of unclassified information. While additional DoD CUI categories are being considered, the specific DoD CUI categories that the noted FOUO information is expected to transition to include: Defense (Material and Munitions): System Name Controlled Technical Information: Center Frequency/Lower Band Limit, Upper Band Limit, Emission Bandwidth, Rx IF Bandwidth Critical Information (Operations Security). Latitude/Longitude, Area of Operation, Alternate Frequency Assignment. | Sensitive | February 21, 2014 DoD CIO Letter to Assistant Secretary of Commerce for Communications and Information concerning determination that this transition plan contains information for which there is a legal basis for nondisclosure and that public disclosure of which would be detrimental to national security, Executive Order 13556: Controlled Unclassified Information, and DoD Manual 5200.01, DoD Information Security Program: Controlled Unclassified Information, Volume 4, February 24, 2012
PGM
N 036003 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 036004 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 044843 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 044844 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 044880 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 044881 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 088081 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 088085 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 095421 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 095427 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 099937 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 099938 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 947215 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 947225 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 948077 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201
N 948097 | Frequency parameters of USN PGM | Classified | 20080728 C5513.2 BENCL113, PMA201

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Availability of Spectrum Relocation Fund (SRF) Funding | All timelines in this plan are based on the assumption that funding will be received three months after the close of the auction. Should the receipt of funds change, timelines may need to be adjusted accordingly.
2 | Availability of Frequency Assignment Authorizations | As described in Tab I, this Transition Plan is based heavily on the DoD Alternative Proposal and its success is critically dependent on the interaction of a number of interdependent elements including those activities of other federal agencies (e.g. DOJ Transition Plan). A number of these elements involve either replacing or modifying systems that will operate in alternate frequency bands. There will be a very large number of new frequency authorizations required in order to support the new operations. New authorizations must be in place prior to existing operations or authorizations being able to be terminated in the 1755-1780 MHz band. Given the large number of new frequency proposals that must be worked through the process and completed, there is concern that all necessary actions can be completed in time to support all of the new operations.
3 | Licensee Coordination With DoD organizations | To preclude any misunderstanding or misinterpretation, potential licensees must be advised that the DoD will provide direction to the military Services and other defense agencies to refer all requests for spectrum relocation information initiated by commercial wireless providers or their agents to the DoD CIO, Spectrum Policy and Program Directorate. The DoD CIO will establish a single focal point that will be responsible for establishing and overseeing procedures to facilitate information exchange between the DoD and wireless licensees.
4 | Availability of Spectrum Relocation Fund (SRF) Funding to provide a Coordination Portal Capability. | The coordination process that wireless licensees will be required to follow includes the DoD requirement to perform associated analyses of potential interference from wireless licensee build-out plans. The DoD will, by necessity, be required to respond to numerous industry coordination requests on specific timelines. This coordination effort will be conducted through a DoD web-based portal capability, which will require time to develop and implement. Given that SRF funding to initiate the development of the DoD portal will not be available until months after the auction and award of licenses, a full coordination capability will not be in operation until early 2016, at the earliest. (Note: A lesson learned from the 1710-1755 MHz auction was that advanced funding to agencies prior to an auction could facilitate enhanced auction revenues and reduced relocation agency timelines. This lesson was the basis for certain language that was incorporated in the Middle Class Tax Relief and Job Creation Act of 2012 which resulted in changes to the Commercial Spectrum Enhancement Act. However, the actual language contained in the Tax Act is such that advanced SRF funding is restricted to a limited set of qualifying costs and are essentially impossible to obtain in a timeframe that actually benefits agencies' advanced preparations for an auction and transition.)
PGM
5 | Limited Government staff to work transition | Delays to the transition may result from limited Government staffing to monitor contract performance and provide technical oversight of transition implementation.
6 | Limited Contractor staff to work transition | Delays to the transition may result from limited Contractor staffing to complete the non-recurring engineering update and the recurring hardware/software retrofit activies.
7 | Timeline to transfer overseas hardware for retrofit | Delays in transfer of overseas hardware from deployed fleet activities my delay the completion of the hardware retrofit.
AMT
8 | Limited manufacturing capacity of vendors of telemetry equipment. | Complete transition may be delayed if manufacturers cannot fullfil equipment orders and provide installation services in a timely manner.
9 | Federal Government procurement delays. | Delays to the transition may result from delays in establishing equipment and service contracts.
10 | Insufficient temporary mobile telemetry ground stations to sustain range telemetry capacity during the transtion. | If temporary mobile telemetry ground stations were not available as required by the Transition Plan, delays to the modification of telemetry ground stations would result and would cause delays to the overall transition out of the band.
11 | Weather Conditions | This transition plan is dependent on installation of new equipment on exterior (outside) aeronautical mobile telemetry sites at the USN NAWC AD Patuxent River MD installation which could be delayed due to extensive winter (cold) and summer (extreme heat index) weather conditions.
12 | Access to Comparable Spectrum (Regulatory) | *****
13 | Technical Solutions | Another primary factor that will limit the implementation of this transition is obtaining the minimum necessary funding (identified in this transition plan) in order to implement the identified mandatory technical solutions in this plan. These technical solutions will increase the spectrum efficiency and multi-band flexibility of the AMT operations in order to meet customer demands at high-density locations like the Navy's premier Research, Development, Test and Evaluation (RDT&E) facilities of the Naval Air Warfare Centers (Aircraft Division - AD; and Weapons Division - WD). These technical solutions are necessary in order to meet these RDT&E requirements with reduced operating bandwidth above 1780 MHz coupled with the other DOD and Federal users now pursuing this same compressed 70 MHz of spectrum.
14 | Spectrum Monitoring Equipment | Spectrum monitoring equipment is a key aspect of the Navy's ability to monitor, locate and enforce spectrum usage in a new severely congested and compressed part of the RF spectrum above 1780 MHz. Additionally, at locations like the NAWCs, spectrum sharing in the 2025 - 2110 MHz will be prevalent and must be monitored to ensure interference free operations for all spectrum users. We will be unable to implement and execute this transition plan without spectrum monitoring and location systems at our installations.
TRR
15 | Ship availability schedules | Installation dependent upon availability of ships to install

## I. Additional Information
*****
For each of the frequency entries within Tab C that are labeled as “Vacate With Temp”, the following stipulation applies. The concept of “temporary sharing” is subject to several conditions. These include: the requirement for the 1755-1780 MHz Early Entry Portal to be operational to handle coordination requests; coordination requests will be addressed on a site-by-site basis and sharing conditions shall be approved by the Military test and/or training range affected; sharing consideration will be assessed based on industry build-out/deployment plans and incumbent DoD operations; and a recognition that industry be aware that sharing may be assessed as not feasible for an extended period of time. Industry should not assume that a label of “Vacate With Temp” indicates that sharing for that frequency is in any way assured. The label only means that DoD is agreeable to determine if sharing is feasible in response to individual industry coordination requests.”
*****
*****
*****
Note 1 (See Tab E)
*****
*****
*****
Note 2(See Tab C)
*****
*****
Note 1 (See Tab C)
*****
PGM
*****
*****
*****
*****
AMT
*****
*****
*****
*****
*****
*****
*****
Additional Considerations:
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
*****
ACTS
*****
*****
*****
*****
TRR
Note 1 (See Tab C)
*****
*****
*****
Note 2 (See Tab C)
*****
Note 3 (See Tab C)
*****
TT&C
*****
*****
*****
*****