## A. Title Page
Department of Interior (DOI) USGS Natural Hazards Transition Plan for the 1755-1780 MHz Band
| Primary Point of Contact: Russell Sveda Office: Office of The Chief Information Officer Telephone Number: 303-236-5091 E-mail: Russell_Sveda@ios.doi.gov |  | Alternate Point of Contact: Mona Singleton Office: U.S. Geological Survey Telephone Number: 703-648-7014 E-mail: msingleton@usgs.gov
Certification regarding Classified and Sensitive Information: I, Russell Sveda, certify that this transition plan is cleared for release to the public and contains no classified or sensitive information.

## B. General Information
1 | This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: |  | Yes
| a. Total pre-auction planning costs: | 0 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer: | 0
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012: | 0
d. This organization attests that:
| [1] To the fullest extent possible, this transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | No
3 | There is additonal information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | No
4 | a. Name of Responsible Officer: | Russell Sveda
| b. Office: | Office of the Chief Information Officer
| c. Telephone Number: | 303-236-5091
| d. E-mail: | russell_sveda@ios.doi.gov
5 | Total Transition Plan Cost ($M): | 35.68

## C. Abstract
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation | Alternate Frequency Assignment | Transition Timeline (Months)
I 096515 | 1760 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 345257N | 1175927W | CA | 344415N | 1173339W | Vacate NO Temp | TBD | 36
I 096511 | 1760 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 334743N | 1173633W | CA | 340810N | 1180739W | Vacate NO Temp | TBD | 36
I 106500 | 1779 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 344415N | 1173339W | CA | 341357N | 1171405W | Vacate NO Temp | TBD | 36
I 116598 | 1779 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 340810N | 1180739W | CA | 334743N | 1173633W | Vacate NO Temp | TBD | 36
I 076525 | 1760 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 355700N | 1205957W | CA | 364537N | 1212928W | Vacate NO Temp | TBD | 36
I 076594 | 1760 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 384552N | 1225042W | CA | 382054N | 1223441W | Vacate NO Temp | TBD | 36
I 076515 | 1763 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 375527N | 1223548W | CA | 375302N | 1221322W | Vacate NO Temp | TBD | 36
I 076521 | 1763 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 370649N | 1215010W | CA | 372720N | 1221022W | Vacate NO Temp | TBD | 36
I 096509 | 1763 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 352337N | 1202100W | CA | 355207N | 1202852W | Vacate NO Temp | TBD | 36
I 076513 | 1779 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 382054N | 1223441W | CA | 375527N | 1223548W | Vacate NO Temp | TBD | 36
I 076523 | 1779 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 364537N | 1212928W | CA | 370649N | 1215010W | Vacate NO Temp | TBD | 36
I 096507 | 1779 |  | 5 | 8 | GG | Microwave | EHZ SEIS |  | CA | 355207N | 1202852W | CA | 355700N | 1205957W | Vacate NO Temp | TBD | 36

## D. Transition Timeline
Timeline (Months after Transition Start)
Serial Number | Geographic Location | Temporary Sharing | Indefinite Sharing | Vacate Assignment
I 096515 | Edwards AFB,CA to Shadow Mtn, CA | No | No | 36
I 096511 | Pleasants Pk,CA to Pasadena, CA | No | No | 36
I 106500 | Shadow Mtn,CA to Strawberry Peak, CA | No | No | 36
I 116598 | Pasadena,CA to Pleasants Pk, CA | No | No | 36
I 076525 | Williams Hill, CA to Fremont Peak, CA | No | No | 36
I 076594 | Geyser Peak, CA to Sonoma Mtn, CA | No | No | 36
I 076515 | Mt Tamalpais, CA to Vollmer Pk, CA | No | No | 36
I 076521 | Crystal Pk, CA to Menlo Park, CA | No | No | 36
I 096509 | Black Mtn, CA to Hog Canyon, CA | No | No | 36
I 076513 | Sonoma Mtn, CA to Mt Tamalpais, CA | No | No | 36
I 076523 | Fremont Pk, CA to Crystal Pk, CA | No | No | 36
I 096507 | Hog Canyon, CA to Williams Hill, CA | No | No | 36

## E. Timeline for Funds
System Name | System ID | Total Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
USGS EHZ SEIS Microwave System | USGS1 | 0 | 0 | 0 | 10.616 | 18.052 | 28.668 | 1 | 48 | 0 | Not Applicable | Not Applicable
USGS Spectrum Relocation Program Office | USGS2 | 0 | 0 | 0 | 0 | 7.012 | 7.012 | 1 | 72 | 0 | Not Applicable | Not Applicable

## F. NTIA Interactions
Interaction required with NTIA to implement this Transition Plan
1 | Alternate frequency assignments will be needed for all eligible assignments listed herein (and their paired duplex channels)
2 | Alternate frequency assignments may need Tx power waivers to reach needed system reliabilty. (mid 2014)
3 | Alternate frequency assignments will be needed for additional stations as described in Tab I and for frequency diversity to reach needed system reliability.
4 | Temporary assignments will be needed in the 1780-1850 MHz Band for sites that are selected for "Fast Track" implementation. (2015)

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference
None

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Jurisdictional approval of new towers and radio sites | Approval processes for construction, leases, permits and other requirements often have indeterminate timeframes when can lead to schedule delays.
2 | Inability to obtain temporary frequencies in the 1780 - 1850 MHz band | Unable to "Fast Track" vacating the 1755-1780 MHz making that spectrum available while the USGS transitions to the 8GHz band.

## I. Additional Information
Executive Summary
As part of the FCC spectrum auction in the fall of 2014, the USGS Seismic Network in California will be required to vacate 12 Radio Frequency Authorizations used in microwave point to point radio links. These radio links are used 24x7x365 to collect real-time life and safety information from hundreds of earthquake sensors in California and the west coast. This network serves the emergency response community, national, state, and local governments, and the public by providing critical real-time information on earthquake locations and magnitudes, ShakeMaps, shaking performance of engineered structures, and data for the California Earthquake Early Warning System. Reliability, security, low maintenance costs, data integrity and environmental/hazard/earthquake resiliency are mission critical requirements of this system.
Complete studies on the impact of transitioning to other frequency bands have not been completed, and no funding or time is available to do so before the required submission of this Transition Plan. Cost estimates will be refined after additional engineering studies are completed upon preauction funding transfer.
Notes for Tab C, column R; Tab D, columns E & F; and Tab E, columns H & J.
The attached Transition Plan assumes that the affected links will be relocated to the 8GHz Band to avoid moving to other planned auction frequency bands, although alternative compatible technical/cost/schedule solutions may be employed as technology allows. As the system is transitioned, additional links will be required, additional equipment will be required, and the potential for interference at 8 GHz is possible. Incremental improvements to the current system design may be undertaken to insure industry standard microwave reliability, security, data integrity and resiliency with low out-year maintenance costs.
Regulatory requirements (permits and modifications to current regulation) will be addressed. IT and data management systems will be modified to accommodate changes to the system.
The USGS could vacate the affected frequencies more quickly ("Fast Track") than planned under the transition to 8GHz by replacing frequency pairs scheduled for auction with temporary frequency pairs in the 1780-1850 MHz band. This would require NTIA to assign new temporary RFAs in this band, re-crystal existing radios, and site visits to each of the impacted microwave sites. Costs for a "Fast Track" approach are not included in this plan due to significant cost increase with moderate schedule acceleration.
An additional 18 frequency links listed below in the upper band (1780-1850 MHz) must also be transitioned to relocate the entire system. These links, together with those in the 1755-1780 band, comprise a single communications system transporting earthquake data. A single system that operated duplex links in both the 1755-1780 and 8GHz bandwidth with different hardware and software would be exceedingly complicated to operate and likely compromise the integrity of the system.
Additional assignments needed outside of eligible frequencies
| Serial # | System Name | Location | Paired Serial # | Frequency (MHz)
| I 096515 | EHZ SEIS | Edwards AFB,CA to Shadow Mtn, CA | I 096514 | 1815
| I 096511 | EHZ SEIS | Pleasants Pk,CA to Pasadena, CA | I 096510 | 1815
| I 106500 | EHZ SEIS | Shadow Mtn,CA to Strawberry Peak, CA | I 106501 | 1830
| I 116598 | EHZ SEIS | Pasadena,CA to Pleasants Pk, CA | I 116599 | 1830
| I 076525 | EHZ SEIS | Williams Hill, CA to Fremont Peak, CA | I 076524 | 1810
| I 076594 | EHZ SEIS | Geyser Peak, CA to Sonoma Mtn, CA | I 076512 | 1810
| I 076515 | EHZ SEIS | Mt Tamalpais, CA to Vollmer Pk, CA | I 076516 | 1815
| I 076521 | EHZ SEIS | Crystal Pk, CA to Menlo Park, CA | I 076520 | 1815
| I 096509 | EHZ SEIS | Black Mtn, CA to Hog Canyon, CA | I 096508 | 1815
| I 076513 | EHZ SEIS | Sonoma Mtn, CA to Mt Tamalpais, CA | I 076514 | 1830
| I 076523 | EHZ SEIS | Fremont Pk, CA to Crystal Pk, CA | I 076522 | 1830
| I 096507 | EHZ SEIS | Hog Canyon, CA to Williams Hill, CA | I 096506 | 1830
| I 076518 | EHZ SEIS | Vollmer Pk to Menlo Park,CA | I 076519 | 1794
| I 076519 | EHZ SEIS | Menlo Park to Vollmer Pk,CA | I 076518 | 1847
| I 096512 | EHZ SEIS | Pleasants Pk to Strawberry Pk, CA | I 096513 | 1794
| I 096513 | EHZ SEIS | Strawberry Pk to Pleasants Pk, CA | I 096512 | 1847
| I 106601 | EHZ SEIS | Williams Hill to Fremont Pk, CA | I 106602 | 1847
| I 106602 | EHZ SEIS | Fremont Pk to Williams Hill, CA | I 106601 | 1810
Notes on Bandwidth specifications (Tab C)
1. Emission Bandwidth (col D) is derived from the emission designator: 5M00G7W (128 TCM digital modulation).
2. Rx IF Bandwidth (col E) is estimated from 8dB adjacent channel rejection specification.