## Title Page
Submitted: 10/25/2017
Approved: 10/25/2017
| First Name | Last Name | Office/Title | Phone Number | E-mail
Responsible Officer | Christina | McCann | Treasury Inspector General for Tax Administration(TIGTA) | 301-210-8729 | Christina.McCann@tigta.treas.gov
Alternate Contact | Marc | Collins | Internal Revenue Service - Criminal Investigation | 918-709-7954 | Marc.Collins@ci.irs.gov
Alternate Contact | William | Kautz | Treasury Inspector General for Tax Administration | 202-236-1964 | william.kautz@tigta.treas.gov

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Alternate Frequency Assignment | Geographic Location associated with Timeline | Sharing Type | Indefinite Sharing Timeline (Months after 1/30/15) | Temporary Sharing Timeline (Months after 1/30/15) | Vacate Assignment Timeline (Months after 1/30/15)
T020185 | TIGTA Techops | 1765 |  | 6 | 6 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | USP | None |  |  | 12
T060040 | CI Techops | 1760 |  | 6 | 6 | Video | USP | USP | xxxxxxx | xxxxxxxx | USP | xxxxxxx | xxxxxxxx | 2200-2290 MHz | USP | None |  |  | 12

## Funds
System Name | Total Pre-Auction Cost ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Cost Pre-2012 ($M) | Equipment Cost ($M) | Deployment Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months) | End Expenditure Timeline (Months) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
CI Techops | 0 | 0 | 0 | 6.521 | 1.04 | 7.561 | 6 | 60 |  |  | Funds required to replace antiquated, analog equipment. The equipment is channelized so is still useable. However, the loss of one frequency cuts down the number of available channels by 33% (1 of 3 available) which diminishes efforts to avoid interference in this very congested band. Procurement of spectrally efficient COFDM equipment will help avoid interference when encountered.
TIGTA Techops | 0 | 0 | 0 | 0.113 | 0.128 | 0.241 | 6 | 12 |  |  | Procurement of replacement digital COFDM microwave equipment and IP-based systems which are more spectrally efficient than the current wideband analog equipment.
Total | 0 | 0 | 0 | 6.634 | 1.168 | 7.802 |  |  | 0

## Interactions
Interaction Name | Interaction Description
1-Obtainning Replacment Frequencies | Additional frequencies are requested in the S Band (2.2-2.29 GHz) to replace the loss of these frequencies.
2- Availablity of Equipment | Potential Delays could occur if there was a lack of available replacement equipment.

## Impact Factors
Factor Name | Factor Description
1 | In order to execute this plan, it is necessary for NTIA to assign fequencies to IRS-CI in the 2.2 to 2.29 GHz range. IRS-CI currently does not have any frequencies in the S band. IRS-CI will be transistioning its existing L band equipment into more spectrally efficient digital COFDM frequencies in the S Band. Commercial services may no longer be a viable option for most operations due to the removal of the unlimited data plans for federal users. Commercial services may continue to be used on a limited basis for very short-term operations. The majority of the transition plan will rely on vacating the L band and switching to the S Band.

## Notes
Note Name | Note Text
Comparable Capability | Although both TIGTA and IRS – CI believe they will be able to vacate the affected frequencies within 12 months of receipt of funding, they both believe it will take up to 5 years (60 months) to reach comparable capability. The reason for this extended time is because the small disguised video transmitter equipment is currently not available and to allow for futher advancement in the microwave arena.

## Excluded Info
Table | Row | Column | Agency Marking | Reference