## General
IPv6 Readiness Tracking Template
v1.2
2011-01-14
Company Name: | [Internet, Inc.]
Process Owner: | [Bob Smith]
[bsmith@internetinc.com]
Business Area Covered By Template: | [Internal (office) IT]
[Factory Floor/Industrial IT]
[External-facing Network Connections]
[Internet-dependent Business Activities]
[Services]
[other]
NOTE:
Depending on the business area that is undergoing a readiness assessment, irrelevant line items on subsequent sheets can be deleted or marked N/A, and new line items can be added.
Please see the accompanying supporting document for additional information on the role of this template in assisting the management of an enterprise to understand the state of an enterprise’s IPv6 readiness.

## Assessing State of Readiness
Assessing the Company's State of Readiness
Status
Not yet started or behind schedule
In Process
Completed or expected to be completed on/ahead of schedule
CATEGORY |  |  | STATUS | OWNER | ORIGINAL EXPECTED COMPLETION DATE | CURRENT EXPECTED COMPLETION DATE | PHASE | COMMENTS
Technical staff should survey and catalogue all aspects of systems that may be impacted by IPv6 deployment
Internal/external IPv6 adress space
Corporate network support for IPv6
Development or updating of policies for the use of IPv6 on corporate networks
Internal/external IPv6 addressing schemes/plans
Internal/external DNS servers (including DHCP servers)
Authentication systems (such as Radius servers)
Use of peering, transit, relays, or tunnels for external connectivity
Management tools for network devices (routers, switches, etc.)
Physical hardware of network devices (routers, switches, etc.)
Service load balancers
Corporate firewalls and VPN concentrators/clients
Corporate storage systems
Corporate video conferencing systems
Corporate VoIP systems
Corporate UPS systems
Client OS deployments
Server OS deployments
Corporate applications
CALEA Support (for carriers)
Security policies and support in network devices & servers
Operations readiness inclusing management systems, troubleshooting & monitoring tools, testing tools
Outsourced (SaaS) applications, including, but not limited to, CRM, HR/talent management, financials, etc.
Associated broadband CPE, such as cable modems, DSL modems, and router/wireless access points
General staff readiness (level of knowledge/expertise)
Identify stakeholders within organization that need to participate in readiness assessment
Purchasing
Ensuring that all new network service providers the company contracts with provide documented support for IPv6
Ensuring that all new network hardware vendors provide documented support for IPv6
Ensuring that all new application platform vendors provide documented support for IPv6
Ensuring that all new software/SaaS/application vendors provide documented support for IPv6
Ensuring the all new vendors/providers be able to provide QA results for IPv6 support, as required/necessary
Internal application developers
Identify embedded/hard-coded reliance on IPv4 connectivity and IPv4 addresses
Identify latency-sensitive or port-intensive applications that would be impacted by NAT implementation outside the company’s control
Ensure appropriate handling of IPv6 addresses within logging, access control, and other relevant subsystems
Corporate Services
Identification of IP-connected embedded devices or systems (microcontrollers, HVAC, etc.) not under the control or management of the technical staff/IT team
Web Site/Content Managers
Documented support for IPv6 by Web hosting provider, if relevant
IPv6 support within underlying Web Server OS
IPv6 support within Web Server software
Can log analysis software handle IPv6 addresses?
Can 3rd party analytics vendor(s) handle IPv6 addresses?
Identify any content on the site (3rd party advertising, store locators, custom offers, weather, etc.) that relies on geolocation of IPv4 addresses
Identify any reliance on IPv4-based whitelists/blacklists
Identify any content that has hard-coded IPv4 addresses
Documented support for IPv6 by CDN provider, if relevant
Sales
Identification , documentation, and escalation of IPv6 requirements from customers, as relevant
Product Management
Development of internal and externally-facing plans and timelines for the support of IPv6 within relevant products and services
Ensure that all software/hardware (as relevant) supportrs IPv6 at parity with IPv4, or is ready to
Document relevant performance metrics
Customer Service/Care
Identify requirements for documentation, troubleshooting processes & tools, escalation paths, etc. related to IPv6 support

## Costs
Costs to Address IPv6-related Issues
Status
Not yet started or behind schedule
In Process
Completed or expected to be completed on/ahead of schedule
CATEGORY |  |  | STATUS | OWNER | ORIGINAL EXPECTED COMPLETION DATE | CURRENT EXPECTED COMPLETION DATE | PHASE | COMMENTS
Time & Effort/Resource requirements for
Comprehensive Survey Development
Roadmap & Timeline Development
Process & Policy Development
Development effort for product/application/service, as relevant
Testing
Training
Ongoing Measurement & Monitoring
[other]
Personnel FTE costs associated with
Hardware Testing
Software Testing
Upgrades
Monitoring
Vendor Negotiations
Application Development/Re-Development
Leadership of Readiness Efforts
Hard [currency] costs associated with
Equipment Testing
Service Testing
Development
Required Upgrades & Enhancements
Training & Education
Salaries
Remaining Exposure Costs for IPv4 Runout
CATEGORY |  |  | STATUS | OWNER | ORIGINAL EXPECTED COMPLETION DATE | CURRENT EXPECTED COMPLETION DATE | PHASE | COMMENTS
Identify date of impact of IPv4 exhaustion
When will company exhaust last IPv4 address space that they were allocated?
Quantify costs to obtain additional needed IPv4 address space after exhaustion
Quantify how many additional IPv4 addresses will be needed
Ascertain availability of needed address space
Identify supplier of needed address space
Identify per-address cost (or range)

## Risks
Risks of Company's IPv6-Related Issues
Status
Not yet started or behind schedule
In Process
Completed or expected to be completed on/ahead of schedule
CATEGORY |  |  | STATUS | OWNER | ORIGINAL EXPECTED COMPLETION DATE | CURRENT EXPECTED COMPLETION DATE | PHASE | COMMENTS
Identify vendor/suppliers with a material relationship, and determine if their lack of timely IPv6 support impacts your company's
Business
Results of Operation
Financial Condition
(NOTE: the USGv6 Test Program template (http://w3.antd.nist.gov/usgv6/sdoc.html) can provide a model for ensuring that suppliers/vendors conform to IPv6 support requirements.)
Identify material/significant customers for whom insufficient IPv6 support by the company could cause material loss of business for the company.
Identify potential third party liability that may arise from insufficient IPv6 support within the company's systems.
Identfify which IPv6-related related risks may be of sufficient importance to investors that they need to be exposed within the company's SEC filings.

## Contingencies & Exposure
IPv6 Contingency Plans
Status
Not yet started or behind schedule
In Process
Completed or expected to be completed on/ahead of schedule
CATEGORY |  |  | STATUS | OWNER | ORIGINAL EXPECTED COMPLETION DATE | CURRENT EXPECTED COMPLETION DATE | PHASE | COMMENTS
Identify & Document Most Reasonably Likely Conflict Scenarios
Identify Costs Associated With Conflict Scenarios
IPv6 Readiness Exposure
CATEGORY |  |  | STATUS | OWNER | ORIGINAL EXPECTED COMPLETION DATE | CURRENT EXPECTED COMPLETION DATE | PHASE | COMMENTS
Identify Business Exposure Related to Lack of IPv6 or NAT Plans
Answer question of "What will the company do if it is not ready..."
...to deal with IPv4 exhaustion
...to support IPv6?