## Title Page
Submitted:
Approved:
| First Name | Last Name | Office/Title | Phone Number | E-mail
Primary Contact | Emily | Campbell | FAA, Office of Program Management | 202-267-7711 | emily.campbell@faa.gov
Responsible Officer | Emily | Campbell | FAA, Office of Program Management | 202-267-7711 | emily.campbell@faa.gov
Alternate Contact | William | Syptak | FAA, Office of Program Management | 202-267-8485 | syptak.william@faa.gov

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth (MHz) | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Frequency Remarks | Geographic Location associated with Timeline (AAO in this column indicates the timeline is associated with the geographic location defined by the Authorized Area of Operation in the frequency assignment) | Sharing Type (Indefinite, Temporary i.e. Coordinated, or None) | Temporary Sharing Timeline (Months After 1/31/2015) | Indefinite Sharing Timeline (Months After 1/31/2015) | Vacate Assignment Timeline (Months After 1/31/2015)
FAA922573 | Elwood ARSR - New Lenox RCO LOW DENSITY RCLT DIGITAL 2 GHZ 97-600 VDM CHANNELS | 1765 |  | 3 | 70 | Microwave | FAA Great Lakes | IL | 412522N | 0880330W | IL | 413253N | 0875653 W | Commercial | FAA Great Lakes | Coordinated | 6 |  | 12

## Funds
System Name | Total Pre-Auction Cost ($M) | Funds Requested Prior to Auction ($M) | Pre-Auction Cost Pre-2012 ($M) | Transition Implementation Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months after Receipt of Funds) | End Expenditure Timeline (Months after Receipt of Funds) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
Elwood ARSR - New Lenox RCO LOW DENSITY RCLT DIGITAL 2 GHZ 97-600 VDM CHANNELS | 0 | 0 | 0 | 0.433 | 0.433 | 3 | 60 |  |  | Replace FAA-owned 2GHz LDRCL with FTI-commercial Last Mile Microwave
Total

## Interactions
Interaction Name | Interaction Description
1 | Interaction required with NTIA to implement this Transition Plan.

## Impact Factors
Factor Name | Factor Description

## Notes
Note Name | Note Text
Executive Summary | FTI Program Office proposes a FTI Last Mile Microwave solution using commercial spectrum to provide telecommunications diversity for the JOL ARSR. The FTI Last Mile Microwave solution will replace the FAA 2GHz LDRCL system currently in place. It is estimated that, once funded, implementation will take approximately 12 months before the FAA LDRCL would be decommissioned.
Paired Assignment | The system is paired with FAA 922572/ M1828.

## Excluded Info
Table | Row | Column | CUI Category | Safeguarding and/or Dissemination Authority