## A. Title Page
Department of Interior (DOI) NPS Video System Transition Plan for the 1755-1780 MHz Band
| Primary Point of Contact: Russell Sveda Office: Office of Chief Information Officer Telephone Number: 303-236-5091 E-mail: russell_sveda@ios.doi.gov |  | Alternate Point of Contact: Major David Mulholland Office: U.S. Park Police Telephone Number: 202-610-5296 E-mail: david_mulholland@nps.gov
Certification regarding Classified and Sensitive Information: I, Russell Sveda, certify that this transition plan, is cleared for release to the public and contains no classified or sensitive information. A separate Annex containing a complete transition plan including all classified and sensitive data is provided under separate cover via authorized channels.

## B. General Information
1 | This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: |  | Yes
| a. Total pre-auction planning costs: | 0.15 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer: | 0.15
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012: | 0
d. This organization attests that:
| [1] To the fullest extent possible, this transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] (Only applicable if the amount in 1b above is greater than $0.00.) Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | No
3 | There is additonal information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | Yes
4 | a. Name of Responsible Officer: | Russell Sveda
| b. (Optional) Office: | Office of the Chief Information Officer
| c. (Optional) Telephone Number: | 303-236-5091
| d. (Optional) E-mail: | russell_sveda@ios.doi.gov
5 | Total Transition Plan Cost ($M): | 8.946

## C. Abstract
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation | Alternate Frequency Assignment | Transition Timeline (Months)
I 065234 | ***** | N/A | 6 | 5 | NPS | Video | ***** | ***** | DC | ***** | ***** | DC | ***** | ***** | Vacate NO Temp | None | 24

## D. Transition Timeline
Timeline (Months after Transition Start)
Serial Number | Geographic Location | Temporary Sharing | Indefinite Sharing | Vacate Assignment
I 065234 | DC | None | None | 24

## E. Timeline for Funds
System Name | System ID | Total Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
***** | NPS | 0.15 | 0.15 | 0 | 6.581 | 2.215 | 8.946 | 6 | 30 | 0.53 | Establish a distribution capability for critical data | Past deployments of this system have revealed vulnernabilities in the dissemination of data. The expanded capability ensures the immediate distribution of critical information to our partner agencies by eliminating that vulnerability.

## F. NTIA Interactions
Interaction required with NTIA to implement this Transition Plan
1 | None anticipated.

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference
I 065234 | The information relates to the U.S. Park Police and the means by which it conducts law enforcement activities in Washington, D.C., and its immediate environs. As such, the legal basis for nondisclosure is 47 U.S.C. § 929(a) and 18 U.S.C. § 2511. The CUI category and subcategory is "Law Enforcement - Communications." | Sensitive | 47 U.S.C. § 929(a) and 18 U.S.C. § 2511

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Sensitive information that is not releasable to the public is excluded in this Transition Plan | While the specific frequency, system and location is not provided to the public, we have included a general location. We will share additional details with qualified bidders under a non-disclosure agreement. The redacted information will not impede fulfillment of the transition plan and should not have a significant impact on the auction since NPS will vacate in 24 months.

## I. Additional Information
*****
During the NPS transition, spectrum sharing within a 90km radius from the center of the District of Columbia (385340.0N, 770233.5W) requires coordination to prevent interference. Sharing beyond the 90 km radius should not require coordination.