## Title Page
Submitted: 7/7/2014
Approved: 12/23/2015
| First Name | Last Name | Office/Title | Phone Number | E-mail
Responsible Officer | James | Mentzer | NOAA Office of Radio Frequency Management | 301-628-5649 | james.mentzer@noaa.gov
Primary Contact | Edna | Prado | NOAA Office of Radio Frequency Management | 301-628-5742 | edna.prado@noaa.gov
Alternate Contact | Ivan | Navarro | NOAA Office of Radio Frequency Management | 301-628-5715 | ivan.navarro@noaa.gov

## Freq-Geo Transition Timeline
Serial Number | System Name | Center Lower Frequency (MHz) | Upper Frequency (MHz) | Emission Bandwidth (MHz) | Receiver Bandwidth | System Use Type Name | Operation Area | Transmitter State | Transmitter Latitude | Transmitter Longitude | Receiver State | Receiver Latitude | Receiver Longitude | Alternate Frequency Assignment | Geographic Location associated with Timeline | Sharing Type | Indefinite Sharing Timeline (Months after 1/30/15) | Temporary Sharing Timeline (Months after 1/30/15) | Vacate Assignment Timeline (Months after 1/30/15)
C121131 | UAV TRAINING | 1768 |  | 5 | 5 | UAS | 7 | FL | 275048N | 0823013W | FL | 275048N | 0823013W | NIB | AAO | None |  |  | 9
C131126 | UAV ENVIRONMENTAL STUDIES | 1768 |  | 5 | 5 | UAS | 81 | FL | 242700N | 0811100W | FL | 242700N | 0811100W | NIB | AAO | None |  |  | 9
C131146 | UAV ENVIRONMENTAL STUDIES | 1758 |  | 5 | 5 | UAS | 50 | LA | 302800N | 0894200W | LA | 302800N | 0894200W | NIB | AAO | None |  |  | 9
C131148 | UAV ENVIRONMENTAL STUDIES | 1765 |  | 5 | 5 | UAS | 22 | AK | 572100N | 1521900W | AK | 572100N | 1521900W | NIB | AAO | None |  |  | 9
C141126 | UAV ENVIRONMENTAL STUDIES | 1759 |  | 5 | 5 | UAS | 3 | MA | 422000N | 0702000W | MA | 422000N | 0702000W | NIB | AAO | None |  |  | 9
C940165 | NEXRAD_MLOS LA | 1767.5 |  | 1.6 | 1.6 | Microwave | Microwave Link | CA | 342442N | 1191043W | CA | 341226N | 1190816W | Commercial | AAO | None |  |  | 16
C940489 | NEXRAD_MLOS MISSOULA | 1767.5 |  | 6 | 6 | Microwave | Microwave Link | MT | 465529N | 1140524W | MT | 470228N | 1135910W | Commercial | AAO | None |  |  | 22

## Funds
System Name | Total Pre-Auction Cost ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Cost Pre-2012 ($M) | Equipment Cost ($M) | Deployment Cost ($M) | Total Cost ($M) | Begin Expenditure Timeline (Months) | End Expenditure Timeline (Months) | Expanded Capability Cost ($M) | Expanded Capability Description | Expanded Capability Justification
NEXRAD_MLOS LA | 0 | 0 | 0 | 0.005 | 0.17 | 0.175 | 6 | 60
NEXRAD_MLOS MISSOULA | 0 | 0 | 0 | 0.005 | 0.17 | 0.175 | 6 | 60
UAV ENVIRONMENTAL STUDIES | 0 | 0 | 0 | 0 | 0 | 0
UAV TRAINING | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0.01 | 0.34 | 0.35 |  |  | 0

## Interactions
Interaction Name | Interaction Description
None | None

## Impact Factors
Factor Name | Factor Description
None | None

## Notes
Note Name | Note Text
1. Summary | The National Weather service has made use of microwave links in the 1755-1780 MHz band for relaying NEXRAD radar data from the radar site(s) to the applicable operations center. This transition plan provides for the replacement of those remaining links with commercially-leased bandwidth.
2. Details | Two remaining sites employ microwave relay links in the band 1755-1780 MHz: Los Angeles/Oxnard, California, and Missoula, Montana. Upon receipt of transition funds, NOAA/NWS will undertake to lease necessary point-to-point bandwidth and remove the associated government-owned microwave equipment. As the currently-installed equipment is considered to have remaining economic lifetime in excess of five-years, NOAA/NWS is seeking reimbursement for estimated installation and recurring lease costs for five years. (The Los Angeles/Oxnard link will be given priority for removal/replacement owing to that region's high rank in the list of economic areas being offered to commercial wireless entities.)
3. Note | For simplicity, the authorized AOA for assignments C131126, C131146, and C131148 is provided in Tab C (column I) as the radius (in km) of a circle centered on the given TX/RX latitude/longitude that circumscribes the actual authorization which was defined by polygons; thus, the actual authorization covers a smaller overall area than implied by the point/circle definition.

## Excluded Info
Table | Row | Column | Agency Marking | Reference