## A. Title Page
Department of Homeland Security (DHS) Transition Plan for the 1755-1780 MHz Band
| Primary Point of Contact: David Campbell Office: Joint Wireless Program Office, Office of the Chief Information Officer Telephone Number: 571-468-9146 E-mail: David.Campbell@HQ.DHS.GOV |  | Alternate Point of Contact: Warren Kendrick Office: Joint Wireless Program Office, Office of the Chief Information Officer Telephone Number: 571-468-9151 E-mail: Warren.Kendrick@HQ.DHS.GOV
Certification regarding Classified and Sensitive Information: I, David Campbell, certify that this transition plan, is cleared for release to the public and contains no classified or sensitive information.

## B. General Information
1 | This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: | Yes | Yes
| a. Total pre-auction planning costs: | 42.982 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer: | 42.982
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012: | 2.9837
d. This organization attests that:
| [1] To the fullest extent possible, this transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] (Only applicable if the amount in 1b above is greater than $0.00.) Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | No
3 | There is additonal information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | No
4 | a. Name of Responsible Officer: | David Campbell
b. (Optional) Office:
c. (Optional) Telephone Number:
d. (Optional) E-mail:
5 | Total Transition Plan Cost ($M): | 490.142

## C. Abstract
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation | Alternate Frequency Assignment | Transition Timeline (Months)
DHS 027456 | 1760.5 |  | 3 | 3 | CBP | Microwave | CBP Microwave | Microwave Link | WA | 474520N | 1172335W | WA | 473429N | 1170451W | Vacate with Temp | 7125-8500 MHz | 36 | TRR
DHS 028258 | 1765 |  | 20 | 20 | ICE | Video | Video 1 | USP | USP | xxxxxxx | xxxxxxx | USP | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42 | PGM | Indefinite
DHS 028259 | 1790 |  | 20 | 20 | ICE | Video | Video 1 | USP | USP | xxxxxxx | xxxxxxx | USP | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42 | Video | Vacate with Temp
DHS 029098 | 1790 |  | 22 | 22 | ICE | Video | Video 1 | DC | DC | xxxxxxx | xxxxxxx | DC | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42 | TT&C | Vacate NO Temp
DHS 029099 | 1790 |  | 22 | 22 | ICE | Video | Video 1 | VA | VA | xxxxxxx | xxxxxxx | VA | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42 | Telemetry
DHS 035558 | 1781 |  | 6 | 6 | ICE | Video | Video 1 | USP | USP | xxxxxxx | xxxxxxx | USP | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42 | Robotics
DHS 038524 | 1775 |  | 6 | 6 | S | Video | Video 2 | USP | USP | xxxxxxx | xxxxxxx | USP | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42 | UAS
DHS 038528 | 1775 |  | 17 | 17 | S | Video | Video 2 | USP | USP | xxxxxxx | xxxxxxx | USP | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42 | Other
DHS 038535 | 1775 |  | 6 | 6 | S | Video | Video 2 | USP | USP | xxxxxxx | xxxxxxx | USP | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42
DHS 040007 | 1770 |  | 6 | 6 | FLTC | Video | Video 3 | 20 | GA | 311502N | 0812834W | GA | 311502N | 0812834W | Vacate with Temp | 2200-2290 MHz | 36
DHS 040063 | 1780 |  | 6 | 6 | FLTC | Video | Video 3 | 20 | GA | 311502N | 0812834W | GA | 311502N | 0812834W | Vacate with Temp | 2200-2290 MHz | 36
DHS 070303 | 1759 |  | 6 | 6 | ICE | Video | Video 1 | USP | USP | xxxxxxx | xxxxxxx | USP | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42
DHS 070652 | 1773 |  | 6 | 6 | ICE | Video | Video 1 | USP | USP | xxxxxxx | xxxxxxx | USP | xxxxxxx | xxxxxxx | Vacate with Temp | 2200-2290 MHz | 42
DHS 125903 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255131N | 0972553W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125904 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255147N | 0972633W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125905 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255227N | 0972651W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125906 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255259N | 0972702W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125907 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255333N | 0972738W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125908 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255326N | 0972807W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125909 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255314N | 0972944W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125910 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255331N | 0972943W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125911 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255408N | 0973011W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125912 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255320N | 0973037W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125913 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255421N | 0973124W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125914 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255440N | 0973120W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125915 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255507N | 0973144W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125916 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255551N | 0973201W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125917 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255606N | 0973235W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125918 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255653N | 0973338W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125919 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255652N | 0973355W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125920 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255739N | 0973436W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125921 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255750N | 0973513W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125922 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255823N | 0973602W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 125923 | 1780 |  | 5 | 5 | CBP | Video | BROWNSVILLE STATION | TX | TX | 255328N | 0972835W | TX | 260114N | 0973025W | Vacate with Temp | 1780-1850 MHz | 36
DHS 142081 | 1757 |  | 3.75 | 3.75 | CBP | Microwave | Microwave Link | NM | NM | 315147N | 1062926W | NM | 314915N | 1064159W | Vacate with Temp | 7125-8500 MHz | 36

## D. Transition Timeline
Timeline (Months after Transition Start)
Serial Number | Geographic Location | Temporary Sharing | Indefinite Sharing | Vacate Assignment
DHS 027456 | WA | 12 | NA | 36
DHS 028258 | USP | 12 | NA | See Tab I
DHS 028259 | USP | 12 | NA | See Tab I
DHS 029098 | DC | 12 | NA | See Tab I
DHS 029099 | VA | 12 | NA | See Tab I
DHS 035558 | USP | 12 | NA | See Tab I
DHS 038524 | USP | 12 | NA | See Tab I
DHS 038528 | USP | 12 | NA | See Tab I
DHS 038535 | USP | 12 | NA | See Tab I
DHS 040007 | GA | 12 | NA | 36
DHS 040063 | GA | 12 | NA | 36
DHS 070303 | USP | 12 | NA | See Tab I
DHS 070652 | USP | 12 | NA | See Tab I
DHS 125903 | TX | 12 | NA | 36
DHS 125904 | TX | 12 | NA | 36
DHS 125905 | TX | 12 | NA | 36
DHS 125906 | TX | 12 | NA | 36
DHS 125907 | TX | 12 | NA | 36
DHS 125908 | TX | 12 | NA | 36
DHS 125909 | TX | 12 | NA | 36
DHS 125910 | TX | 12 | NA | 36
DHS 125911 | TX | 12 | NA | 36
DHS 125912 | TX | 12 | NA | 36
DHS 125913 | TX | 12 | NA | 36
DHS 125914 | TX | 12 | NA | 36
DHS 125915 | TX | 12 | NA | 36
DHS 125916 | TX | 12 | NA | 36
DHS 125917 | TX | 12 | NA | 36
DHS 125918 | TX | 12 | NA | 36
DHS 125919 | TX | 12 | NA | 36
DHS 125920 | TX | 12 | NA | 36
DHS 125921 | TX | 12 | NA | 36
DHS 125922 | TX | 12 | NA | 36
DHS 125923 | TX | 12 | NA | 36
DHS 142081 | NM | 12 | NA | 36

## E. Timeline for Funds
System Name | System ID | Total Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
HQ Project Management | DHS-PM | 9.864 | 9.864 | 2.9837 | 0 | 16.411 | 26.275 | 2015-02-22 | 2021-09-30 | 0 | NA | DHS HQ project management/ oversight
Video 4 OIG | DHS-VS4 | 1.128 | 1.128 | 0 | 2.975 | 2.117 | 6.22 | 2015-02-22 | 2018-02-21 | 0 | NA | Equipment for OIG to conduct internal investigations
CBP Microwave | DHS-M1 | 0.673 | 0.673 | 0 | 1.484 | 2.112 | 4.269 | 2015-02-22 | 2018-02-21 | 0 | NA | Relocatd single TX RX pair in microwave back haul system
Video 1 | DHS-VS1 | 16.367 | 16.367 | 0 | 206.314 | 43.562 | 266.243 | 2015-02-22 | 2020-02-21 | $14.3M | Commercial wired network connectivity for mesh devices to interface with current video management system. Provides for addiitoanl connectivity during transition to Mesh network. | Deployment of Major city law enforcement video surveillance system
Video 2 | DHS-VS2 | 14.277 | 14.277 | 0 | 126.505 | 37.37 | 178.152 | 2015-02-22 | 2020-02-21 | $10.4M | Commercial wired network connectivity for mesh devices to interface with current video management system. Provides for addiitoanl connectivity during transition to Mesh network. | Deployment of Major city law enforcement video surveillance system
Video 3 | DHS -VS3 | 0 | 0 | 0 | 2.455 | 1.121 | 3.576 | 2015-02-22 | 2018-02-21 | 0 | NA | Obtain equipment used by Federal agencies for training purposes
Brownsville Station | DHS-VS5 | 0.673 | 0.673 | 0 | 2.625 | 2.112 | 5.41 | 2015-02-22 | 2018-02-21 | 0 | NA | Reprogram video surveillance system
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## F. NTIA Interactions
Interaction required with NTIA to implement this Transition Plan
1 | Coordination is required to verify GMF data.
2 | Interactions are required to determine the best option from various alternate frequency assignment choices.
3 | Interactions are required to obtain formal approval of new frequency assignments prior to beginning of transition period.

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference
None
Classified
Sensitive

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Funding | Pre-auction funds are provided for technological development of capabilities necessary to relocate into alternative frequncy bands.
2 | Alternate Assignments | Channel assignments for digital video specific channels in the 1675-1695 MHz, 1785-1850, and 2200-2290 MHz bands are granted and will diminish potential interference issues.
3 | Frequency Coordination | Channel assignments are coordinated across the Federal law enfocement community to diminish the potential for interference with a Federal-wide band plan developed.
4 | Technology Development | The necessary development of technologies and devices to support overall surveillance operation relocation will progress to align with transition schedule needs.
5 | Regulatory Criteria | Regulatory criteria will support relocated operations in the alternate bands and policy or legislative changes will be made to ensure adequate priority for surveillance operations in the selected bands.
6 | Federal agency Incumbent Support | In necessary, the incumbents will support interference testing to determine feasibility of co-existence and necessary equipment alterations, and they will support the relocation plan and equipment deployment as necessary to address interference issues. As operations move to other spectrum such as 2200-2290 MHz band there is a potential for interference with incumbent operations which may result in the need for testing of devices to determine means for co-existence. To support this testing the need may arise for agencies to provide equipment for testing at an various locations including independent lab such as ITS boulder. It is not envision that the incumbents would be required to share the testing cost beyond providing the equipment for testing.
7 | Commercial Carrier Coordination | Commercal carriers will coordinate with the Department to minimize mutual interference prio to the department vacating the band as outlined in attachnment I

## I. Additional Information
The Department of Homeland Security (DHS) remains committed to supporting the President’s Spectrum Initiative and has developed this plan as follow-on to the September 2011 report assessing of the Viability of Accommodating Wireless Broadband in the 1755-1850 MHz Band. As noted in the 2011 report, the Department and components use the spectrum being vacated for two primary missions, 1: video surveillance in support of Federal law enforcement operations at Immigration and Customs Enforcement, the US Secret Service, the DHS Office of Inspector General and the Federal Law Enforcement Training facility (training purposes only) and 2: microwave data links connecting remote Customs and Border protection offices. For the video surveillance operations, the Department will utilize spectrum currently assigned in the 2200-2290 MHz, 4400-4940 MHz, and on a limited basis spectrum in the 1780-1850 MHz band. Utilization of existing spectrum in the 2200-2290 and 4400-4940 MHz bands currently shared by other federal law enforcement agencies will allow for increased interoperability of technologies. Operations requiring deep building penetration will be relocated to spectrum favorable to building penetration, e.g. 2200-2290 MHz, and operations with less stringent building penetration requirements will be shifted to the 4400-4940 MHz bands. The strategy of relocating to multiple bands aligns with operational needs and affords the opportunity to mitigate risks associated with relocating to a single candidate band. In addition relocating to spectrum where DHS and other law enforcement agencies currently operate will allow for increased sharing of equipment and technologies. Key to this strategy is the deployment of spectrally efficient digital mesh technologies that allow operations to fit within reduced overall spectrum. The use of digital mesh technologies provide for increased spectrum reuse with a reduced total spectral footprint and thus increase the number of potential uses within a given frequency channel. For the microwave data links, the Department will continue its migration of systems to the 7-8 GHZ band. This approach allows for rapid integration into the systems that were migrated as part of the earlier 1710-1755 MHz exit. The 2011 report the Department’s estimate to vacate the 1755-1780 MHz portion of the 1755-1850 MHZ band was ~$564M. Since the time of the report DHS has worked closely with the Office of Management and Budget, the Department of Justice, the National Telecommunications and Information Administration in developing this plan and preparing for the exit of the 1755-1780 MHz band. As a result of the close working relationship, the Department’s cost estimate has been reduced by ~$74M, a substantial cost savings. To achieve this cost savings, the Department’s strategy consolidates the management of the video operations migration to mesh technologies utilizing an integrated project team with representation from the affected entities, reducing duplication of project management functions. This approach takes into consideration the operational aspects of critical mission capabilities as we migrate to spectrum efficient technologies that are interoperable and sharable with other Federal law enforcement agencies. To successfully execute this plan the following distribution of funds is requested:
|  | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Pre-Auction Transfer Requested ($M) | Equipment and Deployment Related Costs ($M) | Total
| DHS HQ CIO | 2983664.79 | 27101753.28 | 245423154.2269 | 275508572.2969
| ICE HSI | 0 | 6256000 | 135369224.656 | 141625224.656
| USSS TSD | 0 | 4166000 | 49368079.9493 | 53534079.9493
| FLTC | 0 | 0 | 3576050.5041 | 3576050.5041
| DHS OIG | 0 | 1128000 | 5092050.5041 | 6220050.5041
| CBP | 0 | 1346000 | 8332033.8983 | 9678033.8983
| Total | 2983664.79 | 39997753.28 | 447160593.7387 | 490142011.8087
The strategy allows the Department to make available the 1755-1780 MHz spectrum to commercial entities within five years of funding with a more rapid exit of spectrum in priority areas identified by the commercial carries in the CSMAC WG2 report. In addition, the strategy prepares the Department to respond rapidly when and if additional spectrum in the 1780-1850 MHz range is requested.
For the CBP assignments the following assignments are paired: DHS 027456 DHS 027467; DHS 125903 DHS 125902; DHS 125904 DHS 125902; DHS 125905 DHS 125902; DHS 125906 DHS 125902; DHS 125907 DHS 125902; DHS 125908 DHS 125902; DHS 125909 DHS 125902; DHS 125910 DHS 125902; DHS 125911 DHS 125902; DHS 125912 DHS 125902; DHS 125913 DHS 125902; DHS 125914 DHS 125902; DHS 125915 DHS 125902; DHS 125916 DHS 125902; DHS 125917 DHS 125902; DHS 125918 DHS 125902; DHS 125919 DHS 125902; DHS 125920 DHS 125902; DHS 125921 DHS 125902; DHS 125922 DHS 125902; DHS 125923 DHS 125902; DHS 142081 DHS 142080
USP Area Time to Vacate
Ranking | Economic Area |  | Time to Vacate EA (Months) | Associated Major Economic Area
1 | 10 | (NYC-Long Is. NY-NJ-CT-PA-MA-VT) | 30 | 2 (New York City)
2 | 160 | (LA-Riverside-Orange Cnty CA-AZ) | 30 | 44 (Los Angeles-San Diego)
3 | 64 | (Chicago-Gary-Kenosha IL-IN-WI) | 30 | 18 (Chicago)
4 | 131 | (Houston-Galveston-Brazoria TX) | 30 | 31 (Houston)
5 | 31 | (Miami-Fort Lauderdale FL) | 30 | 11 (Miami)
6 | 163 | (San Fran.-Oakland-San Jose CA) | 30 | 43 (San Francisco-Oakland-San Jose)
7 | 158 | (Phoenix-Mesa AZ-NM) | 30 | 40 (Phoenix)
8 | 127 | (Dallas-Fort Worth TX-AR-OK) | 30 | 32 (Dallas-Fort Worth)
9 | 12 | (Phil.-Atl. City PA-NJ-DE-MD) | 30 | 4 (Philadelphia)
10 | 161 | (San Diego CA) | 30 | 44 (Los Angeles-San Diego)
11 | 57 | (Detroit-Ann Arbor-Flint MI) | 30 | 16 (Detroit)
12 | 3 | (Boston-Worcester MA-NH-RI-VT) | 30 | 1 (Northeast)
12 | 3 | (Boston-Worcester MA-NH-RI-VT) | 30 | 1 (Northeast)
13 | 55 | (Cleveland-Akron OH-PA) | 30 | 15 (Cleveland)
14 | 30 | (Orlando FL) | 30 | 10 (Tampa-St. Petersburg-Orlando)
15 | 13 | (Wash.-Balt. DC-MD-VA-WV-PA) | 30 | 5 (Washington)
16 | 170 | (Seattle-Tacoma-Bremerton WA) | 30 | 46 (Seattle)
17 | 34 | (Tampa-St. Petersburg FL) | 30 | 10 (Tampa-St. Petersburg-Orlando)
18 | 49 | (Cincinnati-Hamilton OH-KY-IN) | 30 | 13 (Cincinnati-Dayton)
19 | 40 | (Atlanta GA-AL-NC) | 30 | 8 (Atlanta)
20 | 53 | (Pittsburgh PA-WV) | 30 | 12 (Pittsburgh)
21 | 134 | (San Antonio TX) | 36 | 38 (San Antonio)
22 | 96 | (St. Louis MO-IL) | 36 | 30 (St. Louis)
23 | 67 | (Indianapolis IN-IL) | 36 | 19 (Indianapolis)
24 | 23 | (Charlotte-Gastonia NC-SC) | 36 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
25 | 63 | (Milwaukee-Racine WI) | 36 | 17 (Milwaukee)
26 | 152 | (Salt Lake City-Ogden UT-ID) | 36 | 42 (Salt Lake City)
27 | 107 | (Minneapolis-St. Paul MN-WI-IA) | 36 | 20 (Minneapolis-St. Paul)
28 | 130 | (Austin-San Marcos TX) | 36 | 32 (Dallas-Fort Worth)
28 | 130 | (Austin-San Marcos TX) | 36 | 33 (Dallas-Fort Worth)
29 | 83 | (New Orleans LA-MS) | 36 | 27 (New Orleans-Baton Rouge)
30 | 19 | (Raleigh-Durham-Chapel Hill NC) | 36 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
31 | 141 | (Denver-Boulder CO-KS-NE) | 36 | 33 (Denver)
32 | 153 | (Las Vegas NV-AZ-UT) | 36 | 44 (Los Angeles-San Diego)
33 | 51 | (Columbus OH) | 36 | 14 (Columbus)
34 | 29 | (Jacksonville FL-GA) | 36 | 9 (Jacksonville)
35 | 162 | (Fresno CA) | 36 | 43 (San Francisco-Oakland-San Jose)
36 | 133 | (McAllen-Edinburg-Mission TX) | 36 | 38 (San Antonio)
37 | 172 | (Honolulu HI) | 36 | 48 (Hawaii)
38 | 164 | (Sacramento-Yolo CA) | 36 | 43 (San Francisco-Oakland-San Jose)
39 | 125 | (Oklahoma City OK) | 36 | 37 (Oklahoma City)
40 | 73 | (Memphis TN-AR-MS-KY) | 36 | 26 (Memphis-Jackson)
41 | 70 | (Louisville KY-IN) | 36 | 23 (Louisville-Lexington-Evansville)
42 | 71 | (Nashville TN-KY) | 36 | 25 (Nashville)
43 | 99 | (Kansas City MO-KS) | 36 | 29 (Kansas City)
44 | 20 | (Norfolk-Virginia Beach VA-NC) | 36 | 6 (Richmond)
45 | 167 | (Portland-Salem OR-WA) | 36 | 45 (Portland)
46 | 8 | (Buffalo-Niagara Falls NY-PA) | 36 | 3 (Buffalo)
47 | 78 | (Birmingham AL) | 36 | 24 (Birmingham)
48 | 174 | (Puerto Rico-US Virgin Islands) | 36 | 50 (Puerto Rico and U.S. Virgin Islands)
49 | 18 | (Greensboro-Winston-Salem NC-VA) | 36 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
50 | 32 | (Fort Myers-Cape Coral FL) | 36 | 11 (Miami)
51 | 50 | (Dayton-Springfield OH) | 36 | 13 (Cincinnati-Dayton)
52 | 159 | (Tucson AZ) | 36 | 40 (Phoenix)
53 | 33 | (Sarasota-Bradenton FL) | 36 | 10 (Tampa-St. Petersburg-Orlando)
54 | 118 | (Omaha NE-IA-MO) | 36 | 34 (Omaha)
55 | 84 | (Baton Rouge LA-MS) | 36 | 27 (New Orleans-Baton Rouge)
56 | 15 | (Richmond-Petersburg VA) | 36 | 6 (Richmond)
57 | 41 | (Greenville-Spartanburg SC-NC) | 36 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
58 | 7 | (Rochester NY-PA) | 36 | 2 (New York City)
59 | 157 | (El Paso TX-NM) | 36 | 39 (El Paso-Albuquerque)
60 | 124 | (Tulsa OK-KS) | 36 | 36 (Tulsa)
61 | 104 | (Madison WI-IL-IA) | 36 | 17 (Milwaukee)
62 | 150 | (Boise City ID-OR) | 36 | 42 (Salt Lake City)
63 | 24 | (Columbia SC) | 36 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
64 | 90 | (Little Rock AR) | 36 | 28 (Little Rock)
65 | 26 | (Charleston-North Charleston SC) | 36 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
66 | 44 | (Knoxville TN) | 36 | 22 (Knoxville)
67 | 122 | (Wichita KS-OK) | 36 | 35 (Wichita)
68 | 119 | (Lincoln NE) | 36 | 34 (Omaha)
69 | 156 | (Albuquerque NM-AZ) | 36 | 39 (El Paso-Albuquerque)
70 | 6 | (Syracuse NY-PA) | 36 | 2 (New York City)
70 | 6 | (Syracuse NY-PA) | 36 | 3 (New York City)
71 | 56 | (Toledo OH) | 36 | 16 (Detroit)
72 | 100 | (Des Moines IA-IL-MO) | 36 | 21 (Des Moines-Quad Cities)
73 | 25 | (Wilmington NC-SC) | 36 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
74 | 77 | (Jackson MS-AL-LA) | 36 | 26 (Memphis-Jackson)
75 | 81 | (Pensacola FL) | 36 | 27 (New Orleans-Baton Rouge)
76 | 5 | (Albany-Schenectady-Troy NY) | 36 | 2 (New York City)
77 | 151 | (Reno NV-CA) | 36 | 43 (San Francisco-Oakland-San Jose)
78 | 59 | (Green Bay WI-MI) | 36 | 17 (Milwaukee)
79 | 62 | (Grand Rapids-Muskegon MI) | 36 | 16 (Detroit)
80 | 85 | (Lafayette LA) | 36 | 27 (New Orleans-Baton Rouge)
81 | 80 | (Mobile AL) | 36 | 27 (New Orleans-Baton Rouge)
82 | 166 | (Eugene-Springfield OR-CA) | 36 | 45 (Portland)
83 | 97 | (Springfield IL-MO) | 36 | 18 (Chicago)
84 | 132 | (Corpus Christi TX) | 36 | 38 (San Antonio)
85 | 21 | (Greenville NC) | 36 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
86 | 68 | (Champaign-Urbana IL) | 36 | 18 (Chicago)
87 | 11 | (Harrisburg-Lebanon-Carlisle PA) | 36 | 4 (Philadelphia)
88 | 94 | (Springfield MO) | 36 | 30 (St. Louis)
89 | 35 | (Tallahassee FL-GA) | 36 | 9 (Jacksonville)
90 | 92 | (Fayetteville AR-MO-OK) | 36 | 28 (Little Rock)
91 | 28 | (Savannah GA-SC) | 36 | 8 (Atlanta)
92 | 98 | (Columbia MO) | 36 | 30 (St. Louis)
93 | 74 | (Huntsville AL-TN) | 36 | 24 (Birmingham)
94 | 66 | (Fort Wayne IN) | 36 | 18 (Chicago)
95 | 82 | (Biloxi-Gulfport-Pascagoula MS) | 36 | 27 (New Orleans-Baton Rouge)
96 | 140 | (Pueblo CO-NM) | 36 | 33 (Denver)
97 | 43 | (Chattanooga TN-GA) | 42 | 8 (Atlanta)
98 | 88 | (Shreveport-Bossier City LA-AR) | 42 | 32 (Dallas-Fort Worth)
99 | 65 | (Elkhart-Goshen IN-MI) | 42 | 18 (Chicago)
100 | 69 | (Evansville-Henderson IN-KY-IL) | 42 | 23 (Louisville-Lexington-Evansville)
101 | 2 | (Portland ME) | 42 | 1 (Northeast)
102 | 4 | (Burlington VT-NY) | 42 | 2 (New York City)
103 | 22 | (Fayetteville NC) | 42 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
104 | 87 | (Beaumont-Port Arthur TX) | 42 | 31 (Houston)
105 | 60 | (Appleton-Oshkosh-Neenah WI) | 42 | 17 (Milwaukee)
106 | 39 | (Columbus GA-AL) | 42 | 8 (Atlanta)
107 | 93 | (Joplin MO-KS-OK) | 42 | 29 (Kansas City)
108 | 139 | (Santa Fe NM) | 42 | 39 (El Paso-Albuquerque)
109 | 147 | (Spokane WA-ID) | 42 | 41 (Spokane-Billings)
110 | 135 | (Odessa-Midland TX) | 42 | 32 (Dallas-Fort Worth)
111 | 89 | (Monroe LA) | 42 | 32 (Dallas-Fort Worth)
112 | 27 | (Augusta-Aiken GA-SC) | 42 | 8 (Atlanta)
113 | 101 | (Peoria-Pekin IL) | 42 | 18 (Chicago)
114 | 79 | (Montgomery AL) | 42 | 24 (Birmingham)
115 | 42 | (Asheville NC) | 42 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
116 | 47 | (Lexington KY-TN-VA-WV) | 42 | 23 (Louisville-Lexington-Evansville)
117 | 46 | (Hickory-Morganton NC-TN) | 42 | 7 (Charlotte-Greensboro-Greenville-Raleigh)
118 | 136 | (Hobbs NM-TX) | 42 | 39 (El Paso-Albuquerque)
119 | 154 | (Flagstaff AZ-UT) | 42 | 40 (Phoenix)
120 | 137 | (Lubbock TX) | 42 | 32 (Dallas-Fort Worth)
121 | 54 | (Erie PA) | 42 | 15 (Cleveland)
122 | 14 | (Salisbury MD-DE-VA) | 42 | 5 (Washington)
123 | 38 | (Macon GA) | 42 | 8 (Atlanta)
124 | 86 | (Lake Charles LA) | 42 | 31 (Houston)
125 | 129 | (San Angelo TX) | 42 | 32 (Dallas-Fort Worth)
126 | 148 | (Idaho Falls ID-WY) | 42 | 42 (Salt Lake City)
127 | 1 | (Bangor ME) | 42 | 1 (Northeast)
128 | 123 | (Topeka KS) | 42 | 29 (Kansas City)
129 | 103 | (Cedar Rapids IA) | 42 | 21 (Des Moines-Quad Cities)
130 | 106 | (Rochester MN-IA-WI) | 42 | 20 (Minneapolis-St. Paul)
131 | 105 | (La Crosse WI-MN) | 42 | 17 (Milwaukee)
132 | 138 | (Amarillo TX-NM) | 42 | 32 (Dallas-Fort Worth)
133 | 165 | (Redding CA-OR) | 42 | 43 (San Francisco-Oakland-San Jose)
134 | 45 | (Johnson City-Kingsport TN-VA) | 42 | 22 (Knoxville)
135 | 36 | (Dothan AL-FL-GA) | 42 | 24 (Birmingham)
136 | 9 | (State College PA) | 42 | 12 (Pittsburgh)
137 | 37 | (Albany GA) | 42 | 8 (Atlanta)
138 | 17 | (Roanoke VA-NC-WV) | 42 | 6 (Richmond)
139 | 169 | (Richland-Kennewick-Pasco WA) | 42 | 46 (Seattle)
140 | 75 | (Tupelo MS-AL-TN) | 42 | 26 (Memphis-Jackson)
141 | 61 | (Traverse City MI) | 42 | 16 (Detroit)
142 | 91 | (Fort Smith AR-OK) | 42 | 28 (Little Rock)
143 | 109 | (Duluth-Superior MN-WI) | 42 | 20 (Minneapolis-St. Paul)
144 | 128 | (Abilene TX) | 42 | 32 (Dallas-Fort Worth)
145 | 76 | (Greenville MS) | 42 | 26 (Memphis-Jackson)
146 | 143 | (Casper WY-ID-UT) | 42 | 33 (Denver)
147 | 149 | (Twin Falls ID) | 42 | 42 (Salt Lake City)
148 | 126 | (Western Oklahoma OK) | 42 | 37 (Oklahoma City)
149 | 16 | (Staunton VA-WV) | 42 | 6 (Richmond)
150 | 48 | (Charleston WV-KY-OH) | 42 | 13 (Cincinnati-Dayton)
151 | 116 | (Sioux Falls SD-IA-MN-NE) | 42 | 20 (Minneapolis-St. Paul)
152 | 113 | (Fargo-Moorhead ND-MN) | 42 | 20 (Minneapolis-St. Paul)
153 | 95 | (Jonesboro AR-MO) | 42 | 28 (Little Rock)
154 | 108 | (Wausau WI) | 42 | 17 (Milwaukee)
155 | 102 | (Davenport-Moline IA-IL) | 42 | 21 (Des Moines-Quad Cities)
156 | 142 | (Scottsbluff NE-WY) | 42 | 33 (Denver)
157 | 52 | (Wheeling WV-OH) | 42 | 12 (Pittsburgh)
158 | 144 | (Billings MT-WY) | 42 | 41 (Spokane-Billings)
159 | 168 | (Pendleton OR-WA) | 42 | 41 (Spokane-Billings)
160 | 115 | (Rapid City SD-MT-NE-ND) | 42 | 33 (Denver)
161 | 110 | (Grand Forks ND-MN) | 42 | 20 (Minneapolis-St. Paul)
162 | 117 | (Sioux City IA-NE-SD) | 42 | 21 (Des Moines-Quad Cities)
163 | 155 | (Farmington NM-CO) | 42 | 39 (El Paso-Albuquerque)
164 | 112 | (Bismarck ND-MT-SD) | 42 | 20 (Minneapolis-St. Paul)
165 | 72 | (Paducah KY-IL) | 42 | 23 (Louisville-Lexington-Evansville)
166 | 171 | (Anchorage AK) | 42 | 47 (Alaska)
167 | 120 | (Grand Island NE) | 42 | 34 (Omaha)
168 | 146 | (Missoula MT) | 42 | 41 (Spokane-Billings)
169 | 58 | (Northern Michigan MI) | 42 | 16 (Detroit)
170 | 111 | (Minot ND) | 42 | 20 (Minneapolis-St. Paul)
171 | 114 | (Aberdeen SD) | 42 | 20 (Minneapolis-St. Paul)
172 | 145 | (Great Falls MT) | 42 | 41 (Spokane-Billings)
173 | 121 | (North Platte NE-CO) | 42 | 34 (Omaha)
174 | 173 | (Guam-Northern Mariana Islands) | 42 | 49 (Guam and the Northern Mariana Islands)
175 | 175 | (American Samoa) | 42 | 51 (American Samoa)
176 | 176 | (Gulf of Mexico) | 42 | 52 (Gulf of Mexico)