## A. Title Page
Department of the interior (DOI) Metrological Satellite Systems Transition Plan for the 1695-1710 MHz Band
| Primary Point of Contact: Bryan L. Wright Office: Office of the Chief Information Officer Telephone Number: 703-648-5547 E-mail: bryan_wright@ios.doi.gov |  | Alternate Point of Contact: Russell Sveda Office: Office of Chief Infromation Officer Telephone Number: 303-236-5091 E-mail: russell_sveda@ios.doi.gov
Certification regarding Classified and Sensitive Information: I, Russell Sveda, certify that this transition plan, is cleared for release to the public and contains no classified or sensitive information.

## B. General Information
1 | This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: |  | Yes
| a. Total pre-auction planning costs ($M): | 0.155 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer ($M): | 0.155
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012 ($M): | 0.06
d. This organization attests that:
| [1] To the fullest extent possible, this transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] (Only applicable if the amount in 1b above is greater than $0.00.) Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | No
3 | There is additonal information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | No
4 | a. Name of Responsible Officer: | Russell Sveda
| b. (Optional) Office: | DOI OCIO
| c. (Optional) Telephone Number: | 303-236-5091
| d. (Optional) E-mail: | russell_sveda@ios.doi.gov
5 | Total Transition Plan Cost ($M): | 34.325

## C. Abstract
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation | Alternate Frequency Assignment | Transition Timeline (Months)
DOC 860055 | 1702.5 |  | 1.328 | 1.328 | USGS | MetSat | Sioux Falls, SD - POES (RRC EROSLRPS) | Sioux Falls, SD | NGSO | NGSO | NGSO | SD | 433409N | 0963733W | Indefinite | NONE | 39
DOC 860056 | 1707 |  | 1.328 | 1.328 | USGS | MetSat | Sioux Falls, SD - POES (RRC EROSLRPS) | Sioux Falls, SD | NGSO | NGSO | NGSO | SD | 433409N | 0963733W | Indefinite | NONE | 39
DOC 860054 | 1698 |  | 1.328 | 1.328 | USGS | MetSat | Sioux Falls, SD - POES (RRC EROSLRPS) | Sioux Falls, SD | NGSO | NGSO | NGSO | SD | 433409N | 0963733W | Indefinite | NONE | 39
DOC 850523 | 1694.8 |  | 4 | 2.2 | USGS | MetSat | Sioux Falls, SD - GOES (RRC EDDN-1) | Sioux Falls, SD | GSO | 000000N | 0750000W | SD | 434406N | 0963732W | Indefinite | NONE | 39
DOC 850522 | 1694.5 |  | 4 | 2.2 | USGS | MetSat | Sioux Falls, SD - GOES (RRC EDDN-1) | Sioux Falls, SD | GSO | 000000N | 0750000W | SD | 434406N | 0963732W | Indefinite | NONE | 39
DOC 850543 | 1694.8 |  | 4 | 2.2 | USGS | MetSat | Sioux Falls, SD - GOES (RRC EDDN-2) | Sioux Falls, SD | GSO | 000000N | 1350000W | SD | 434418N | 0963737W | Indefinite | NONE | 39
DOC 850542 | 1694.5 |  | 4 | 2.2 | USGS | MetSat | Sioux Falls, SD - GOES (RRC EDDN-2) | Sioux Falls, SD | GSO | 000000N | 1350000W | SD | 434418N | 0963737W | Indefinite | NONE | 39
DOC 850543 | 1694.8 |  | 4 | 2.2 | BLM | MetSat | Boise, ID - GOES (RRC NFIC) | Boise, ID | GSO | 000000N | 1350000W | ID | 433403N | 1161240W | Indefinite | NONE | 39
DOC 850542 | 1694.5 |  | 4 | 2.2 | BLM | MetSat | Boise, ID - GOES (RRC NFIC) | Boise, ID | GSO | 000000N | 1350000W | ID | 433403N | 1161240W | Indefinite | NONE | 39
DOC 850523 | 1694.8 |  | 4 | 2.2 | BOR | MetSat | Boise, ID - GOES (RRC BORPNRHA) | Boise, ID | GSO | 000000N | 0750000W | ID | 433653N | 1161508W | Indefinite | NONE | 39
DOC 850522 | 1694.5 |  | 4 | 2.2 | BOR | MetSat | Boise, ID - GOES (RRC BORPNRHA) | Boise, ID | GSO | 000000N | 0750000W | ID | 433653N | 1161508W | Indefinite | NONE | 39
DOC 850523 | 1694.8 |  | 4 | 2.2 | USGS | MetSat | Guaynabo, PR - GOES (RRC CWSC) | Guaynabo, PR | GSO | 000000N | 0750000W | PR | 182526N | 0660650W | Indefinite | NONE | 39
DOC 850522 | 1694.5 |  | 4 | 2.2 | USGS | MetSat | Guaynabo, PR - GOES (RRC CWSC) | Guaynabo, PR | GSO | 000000N | 0750000W | PR | 182526N | 0660650W | Indefinite | NONE | 39
DOC 850523 | 1694.8 |  | 4 | 2.2 | TVA | MetSat | Knoxville, TN - GOES (RRC TVARFC) | Knoxville, TN | GSO | 000000N | 0750000W | TN | 355758W | 0835513W | Indefinite | NONE | 39
DOC 850522 | 1694.5 |  | 4 | 2.2 | TVA | MetSat | Knoxville, TN - GOES (RRC TVARFC) | Knoxville, TN | GSO | 000000N | 0750000W | TN | 355758W | 0835513W | Indefinite | NONE | 39

## D. Transition Timeline
Timeline (Months after Transition Start)
Serial Number | Geographic Location | Temporary Sharing | Indefinite Sharing | Vacate Assignment
DOC 860055 | SD Sioux Falls |  | 39 | N/A
DOC 860056 | SD Sioux Falls |  | 39 | N/A
DOC 860054 | SD Sioux Falls |  | 39 | N/A
DOC 850523 | SD Sioux Falls |  | 39 | N/A
DOC 850522 | SD Sioux Falls |  | 39 | N/A
DOC 850543 | SD Sioux Falls |  | 39 | N/A
DOC 850542 | SD Sioux Falls |  | 39 | N/A
DOC 850543 | ID Boise |  | 39 | N/A
DOC 850542 | ID Boise |  | 39 | N/A
DOC 850523 | ID Boise |  | 39 | N/A
DOC 850522 | ID Boise |  | 39 | N/A
DOC 850523 | PR Guaynabo |  | 39 | N/A
DOC 850522 | PR Guaynabo |  | 39 | N/A
DOC 850523 | TN Knoxville |  | 39 | N/A
DOC 850522 | TN Knoxville |  | 39 | N/A

## E. Timeline for Funds
System Name | System ID | Total Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
Sioux Falls, SD - POES Sioux Falls, SD - GOES Sioux Falls, SD - GOES | (RRC EROSLRPS) (RRC EDDN-1) (RRC EDDN-2) | 0.031 | 0.031 | 0.012 | 7.372 | 2.641 | 10.044 | 1 month | 75 months
Boise, ID - GOES | (RRC NIFC) | 0.031 | 0.031 | 0.012 | 3.476 | 1.873 | 5.38 | 1 month | 75 months |  |  | Boise sites are not co-located
Boise, ID - GOES | (RRC BORPNRHA) | 0.031 | 0.031 | 0.012 | 3.476 | 1.873 | 5.38 | 1 month | 75 months |  |  | Boise sites are not co-located
Guaynabo, PR - GOES | (RRC CWSC) | 0.031 | 0.031 | 0.012 | 6.038 | 2.12 | 8.189 | 1 month | 75 months
Knoxville, TN - GOES | (RRC TVARFC) | 0.031 | 0.031 | 0.012 | 3.374 | 1.927 | 5.332 | 1 month | 75 months

## F. NTIA Interactions
Interaction required with NTIA to implement this Transition Plan
1 | Engage ITS Boulder to setup sharing coordination portal
2 | Faciliate enforcement should interference above allowable levels occur at MetSat downlink sites discovered during monitoring
3 | Facilitate coordination with FCC in developing initial coordination agreements and dealing with enforcement issues relative to band sharing arrangements

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference
None

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Technology/Development | Adequate and proper phasing of funds will be required to enable development of capabilities necessary to allow sharing of spectrum in accordance with legislation.
2 | Frequency Sharing Coordination | Ability to validate entities' methodologies for sharing.
3 | Regulatory Criteria | Regulatory criteria will provide private sector user incentive to not interfere with Federal stations without jeopardizing DOI/TVA ability to complete the mission and/or execute its primary mission essential functions.
4 | Incumbent Support | Incumbents will support interference testing to determine feasibility of co-existence and necessary equipment alterations, and they will support the relocation plan and equipment deployment as necessary to address interference issues.

## I. Additional Information
This transition plan identifies all the required actions and costs needed to make the 1695-1710 MHz band available for auction for shared use with wireless broadband providers. In the establishment of protection distances around critical DOI and TVA MetSat locations used to receive environmental sensor data, DOI plans to install monitoring capabilities at each of the receiver locations to ensure compliance with the interference threshold criteria established by the FCC and to provide the ability to identify and mitigate any interference experienced from the wireless broadband providers in the shared band. This plan includes 3 years of Operations and Maintenance (O&M) after the monitoring is deployed and supports cost sharing for the compliance monitoring development by DOC/NOAA. DOI also supports and is planning on the establishment of a spectrum coordination portal developed by ITS-Boulder. This portal development is in conjunction with the DOC/NOAA and DOD to facilitate the successful coordination between the AWS licensees and federal agencies of sharing arrangements now and into the future. This plan includes costs for a cost-sharing of the total cost for the portal development and 3 years of O&M.