## A. Title Page
Department of Justice (DOJ) Transition Plan for the 1755-1780 MHz Band
| Primary Point of Contact: Richard Von Bostel Office: DOJ Wireless Management Office Telephone Number: 202-616-1167 E-mail: richard.a.vonbostel@usdoj.gov |  | Alternate Point of Contact: Michael Gilmore Office: Next Generation Wireless Office Telephone Number: 202-439-0951 E-mail: michael.gilmore@ic.fbi.gov
Certification regarding Classified and Sensitive Information: I, Michael Gilmore, certify that this transition plan, is cleared for release to the public and contains no classified or sensitive information. A separate Annex containing a complete transition plan including all classified and sensitive data is provided under separate cover via authorized channels.
4/30/2014 Version Revised TP; admin corrections on 6/19/2014, 07/01/2014, and 07/14/2014

## B. General Information
1 | This Transition Plan includes pre-auction planning costs, as defined in Section O.2 of Annex O: |  | Yes
| a. Total pre-auction planning costs: | 2.221 | No
| b. The subtotal amount, if any, of pre-auction planning costs requested for pre-auction transfer: | 2.221
| c. The subtotal amount, if any, of pre-auction planning costs incurred after June 28, 2010, but before February 22, 2012: | 0
d. This organization attests that:
| [1] This transition plan provides for sharing and coordination of eligible frequencies with non-federal users, including reasonable accommodation for the use of eligible frequencies by non-federal users during the transition period. | Yes
| [2] This transition plan provides for non-federal users to be able to use eligible frequencies during the transition period in geographic areas where this organization does not use such frequencies. | Yes
| [3] During the transition period, this organization will make itself available for negotiation and discussion with non-federal users not later than 30 days after a written request. | Yes
| [4] During the transition period, this organization will make available to a non-federal user with appropriate security clearances any classified information regarding the relocation process, on a need-to-know basis. | Yes
| [5] (Only applicable if the amount in 1b above is greater than $0.00.) Funds transferred before an auction likely allow for timely implementation of relocation or sharing, thereby increasing net expected auction proceeds by an amount not less than the time value of the amount of funds transferred. | Yes
2 | There is additional information required to be included in the Transition Plan that is not included in this document because it is classified information, as defined in Section O.7 of Annex O. | No
3 | There is additional information required to be included in the Transition Plan that is not included in this document because it is sensitive information, as defined in Section O.7 of Annex O. | Yes
4 | a. Name of Responsible Officer: | Michael Gilmore
| b. (Optional) Office: | FBI
| c. (Optional) Telephone Number: | 202-439-0951
| d. (Optional) E-mail: | michael.gilmore@ic.fbi.gov
5 | Total Transition Plan Cost ($M): | 1104.3303

## C. Abstract
Serial Number | Center Freq./ Lower Band Limit (MHz) | Upper Band Limit (MHz) (if appl) | Emission Bandwidth (20 dB) (MHz) | Rx IF Bandwidth (3 dB) (MHz) | Bureau | System Use | System Name | Authorized Area of Operation | TX State | TX Latitude | TX Longitude | RX State | RX Latitude | RX Longitude | Sharing/ Relocation | Alternate Frequency Assignment | Transition Timeline (Months)
J 052221 | ***** |  | ***** | 18 | ***** | Microwave | Mobile |  | AL | ***** | ***** | AL | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 053257 | ***** |  | ***** | 18 | ***** | Microwave | Birmingham |  | AL | ***** | ***** | AL | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 062013 | ***** |  | ***** | 18 | ***** | Microwave | Phoenix |  | AZ | ***** | ***** | AZ | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 042278 | ***** |  | ***** | 18 | ***** | Microwave | San Diego |  | CA | ***** | ***** | CA | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 042201 | ***** |  | ***** | 18 | ***** | Microwave | Baltimore1 |  | DE | ***** | ***** | DE | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 053717 | ***** |  | ***** | 18 | ***** | Microwave | Baltimore2 |  | MD | ***** | ***** | MD | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 062689 | ***** |  | ***** | 18 | ***** | Microwave | Jacksonville |  | FL | ***** | ***** | FL | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 073001 | ***** |  | ***** | 18 | ***** | Microwave | Miami |  | FL | ***** | ***** | FL | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 042351 | ***** |  | ***** | 18 | ***** | Microwave | New Orleans |  | LA | ***** | ***** | LA | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 062575 | ***** |  | ***** | 18 | ***** | Microwave | Detroit |  | MI | ***** | ***** | MI | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 042307 | ***** |  | ***** | 18 | ***** | Microwave | Minneapolis |  | MN | ***** | ***** | MN | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 064554 | ***** |  | ***** | 18 | ***** | Microwave | Buffalo |  | NY | ***** | ***** | NY | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 052207 | ***** |  | ***** | 18 | ***** | Microwave | Oklahoma City1 |  | OK | ***** | ***** | OK | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 052208 | ***** |  | ***** | 18 | ***** | Microwave | Oklahoma City2 |  | OK | ***** | ***** | OK | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 053308 | ***** |  | ***** | 18 | ***** | Microwave | Portland1 |  | OR | ***** | ***** | OR | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 062594 | ***** |  | ***** | 18 | ***** | Microwave | Portland2 |  | OR | ***** | ***** | OR | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 053700 | ***** |  | ***** | 18 | ***** | Microwave | Knoxville |  | TN | ***** | ***** | TN | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 043969 | ***** |  | ***** | 18 | ***** | Microwave | Houston |  | TX | ***** | ***** | TX | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 053791 | ***** |  | ***** | 18 | ***** | Microwave | Dallas |  | TX | ***** | ***** | TX | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 042229 | ***** |  | ***** | 18 | ***** | Microwave | Washington, DC |  | VA | ***** | ***** | VA | ***** | ***** | Vacate NO Temp | C/X Band | 30
J 032216 | ***** |  | ***** | 18 | ***** | Robotics | Operational1 | USP | USP | ***** | ***** | USP | ***** | ***** | Vacate with Temp | S/C Band | 30
J 991007 | ***** |  | ***** | 18 | ***** | Robotics | Operational2 | USP | USP | ***** | ***** | USP | ***** | ***** | Vacate with Temp | S/C Band | 30
J 951326 | ***** |  | ***** | 18 | ***** | Video | Surveillance1 | USP | USP | ***** | ***** | USP | ***** | ***** | Vacate with Temp | L/S/C Band | 42
J 055907 | ***** |  | ***** | 11 | ***** | Video | Surveillance2 | USP | USP | ***** | ***** | USP | ***** | ***** | Vacate with Temp | L/S/C Band | 42
J 055908 | ***** |  | ***** | 11 | ***** | Video | Surveillance3 | USP | USP | ***** | ***** | USP | ***** | ***** | Vacate with Temp | L/S/C Band | 42
J 114544 | ***** |  | ***** | 8 | ***** | UAS | Operational3 | 80 KM | CO | ***** | ***** | CO | ***** | ***** | Vacate NO Temp | S/C Band | 30
J 114546 | ***** |  | ***** | 8 | ***** | UAS | Operational4 | 80 KM | TX | ***** | ***** | TX | ***** | ***** | Vacate NO Temp | S/C Band | 30
J 112602 | ***** |  | ***** | 8 | ***** | UAS | Operational5 | 80 KM | TX | ***** | ***** | TX | ***** | ***** | Vacate NO Temp | S/C Band | 30
J 142505 | ***** |  | ***** | 8 | ***** | UAS | Operational6 | 80 KM | VA | ***** | ***** | VA | ***** | ***** | Vacate NO Temp | S/C Band | 30
J 112600 | ***** |  | ***** | 8 | ***** | UAS | Operational7 | 80 KM | VA | ***** | ***** | VA | ***** | ***** | Vacate NO Temp | S/C Band | 30
J 039004 | ***** |  | ***** | 11 | ***** | Video | Surveillance4 | USP | USP | ***** | ***** | USP | ***** | ***** | Vacate with Temp | L/S/C Band | 42
J 071082 | ***** |  | ***** | 11 | ***** | Video | Surveillance5 | USP | USP | ***** | ***** | USP | ***** | ***** | Vacate with Temp | L/S/C Band | 42
J 904426 | ***** |  | ***** | 11 | ***** | Video | Surveillance6 | USP | USP | ***** | ***** | USP | ***** | ***** | Vacate with Temp | L/S/C Band | 42

## D. Transition Timeline
Timeline (Months after Transition Start)
Serial Number | Geographic Location (Service Area) | Begin Temporary Sharing | Begin Indefinite Sharing | Vacate Assignment
J 032216 | Washington DC Region | 27 |  | 39
J 032216 | Florida Region | 27 |  | 39
J 032216 | Northeast Region | 27 |  | 39
J 032216 | Atlanta Region | 28 |  | 40
J 032216 | Chicago Region | 28 |  | 40
J 032216 | New Orleans Region | 28 |  | 40
J 032216 | Detroit Region | 29 |  | 41
J 032216 | Texas Region | 29 |  | 41
J 032216 | St. Louis Region | 29 |  | 41
J 032216 | Seattle Region | 30 |  | 42
J 032216 | New York Region | 30 |  | 42
J 032216 | California Region | 30 |  | 42
J 991007 | Washington DC Region | 27 |  | 39
J 991007 | Florida Region | 27 |  | 39
J 991007 | Northeast Region | 27 |  | 39
J 991007 | Atlanta Region | 28 |  | 40
J 991007 | Chicago Region | 28 |  | 40
J 991007 | New Orleans Region | 28 |  | 40
J 991007 | Detroit Region | 29 |  | 41
J 991007 | Texas Region | 29 |  | 41
J 991007 | St. Louis Region | 29 |  | 41
J 991007 | Seattle Region | 30 |  | 42
J 991007 | New York Region | 30 |  | 42
J 991007 | California Region | 30 |  | 42
J 951326 | Washington DC Region | 27 |  | 39
J 951326 | Florida Region | 27 |  | 39 | J 951326 | Washington DC Region | 39 | J 055907 | USP | 42
J 951326 | Northeast Region | 27 |  | 39 | J 951326 | Florida Region | 39 | J 055908 | USP | 42
J 951326 | Atlanta Region | 28 |  | 40 | J 951326 | Northeast Region | 39 | J 114544 | Colorado | 30
J 951326 | Chicago Region | 28 |  | 40 | J 951326 | Atlanta Region | 40 | J 114546 | Texas | 30
J 951326 | New Orleans Region | 28 |  | 40 | J 951326 | Chicago Region | 40 | J 112602 | Texas | 30
J 951326 | Detroit Region | 29 |  | 41 | J 951326 | New Orleans Region | 40 | J 112599 | Virginia | 30
J 951326 | Texas Region | 29 |  | 41 | J 951326 | Detroit Region | 41 | J 112600 | Virginia | 30
J 951326 | St. Louis Region | 29 |  | 41 | J 951326 | Texas Region | 41 | J 039004 | USP | 42
J 951326 | Seattle Region | 30 |  | 42 | J 951326 | St. Louis Region | 41 | J 071082 | USP | 42
J 951326 | New York Region | 30 |  | 42 | J 951326 | Seattle Region | 42 | J 904426 | USP | 42
J 951326 | California Region | 30 |  | 42 | J 951326 | New York Region | 42
J 055907 | Washington DC Region | 27 |  | 39 | J 951326 | California Region | 42
J 055907 | Florida Region | 27 |  | 39
J 055907 | Northeast Region | 27 |  | 39
J 055907 | Atlanta Region | 28 |  | 40
J 055907 | Chicago Region | 28 |  | 40
J 055907 | New Orleans Region | 28 |  | 40
J 055907 | Detroit Region | 29 |  | 41
J 055907 | Texas Region | 29 |  | 41
J 055907 | St. Louis Region | 29 |  | 41
J 055907 | Seattle Region | 30 |  | 42
J 055907 | New York Region | 30 |  | 42
J 055907 | California Region | 30 |  | 42
J 055908 | Washington DC Region | 27 |  | 39
J 055908 | Florida Region | 27 |  | 39
J 055908 | Northeast Region | 27 |  | 39
J 055908 | Atlanta Region | 28 |  | 40
J 055908 | Chicago Region | 28 |  | 40
J 055908 | New Orleans Region | 28 |  | 40
J 055908 | Detroit Region | 29 |  | 41
J 055908 | Texas Region | 29 |  | 41
J 055908 | St. Louis Region | 29 |  | 41
J 055908 | Seattle Region | 30 |  | 42
J 055908 | New York Region | 30 |  | 42
J 055908 | California Region | 30 |  | 42
J 039004 | Washington DC Region | 27 |  | 39
J 039004 | Florida Region | 27 |  | 39
J 039004 | Northeast Region | 27 |  | 39
J 039004 | Atlanta Region | 28 |  | 40
J 039004 | Chicago Region | 28 |  | 40
J 039004 | New Orleans Region | 28 |  | 40
J 039004 | Detroit Region | 29 |  | 41
J 039004 | Texas Region | 29 |  | 41
J 039004 | St. Louis Region | 29 |  | 41
J 039004 | Seattle Region | 30 |  | 42
J 039004 | New York Region | 30 |  | 42
J 039004 | California Region | 30 |  | 42
J 071082 | Washington DC Region | 27 |  | 39
J 071082 | Florida Region | 27 |  | 39
J 071082 | Northeast Region | 27 |  | 39
J 071082 | Atlanta Region | 28 |  | 40
J 071082 | Chicago Region | 28 |  | 40
J 071082 | New Orleans Region | 28 |  | 40
J 071082 | Detroit Region | 29 |  | 41
J 071082 | Texas Region | 29 |  | 41
J 071082 | St. Louis Region | 29 |  | 41
J 071082 | Seattle Region | 30 |  | 42
J 071082 | New York Region | 30 |  | 42
J 071082 | California Region | 30 |  | 42
J 904426 | Washington DC Region | 27 |  | 39
J 904426 | Florida Region | 27 |  | 39
J 904426 | Northeast Region | 27 |  | 39
J 904426 | Atlanta Region | 28 |  | 40
J 904426 | Chicago Region | 28 |  | 40
J 904426 | New Orleans Region | 28 |  | 40
J 904426 | Detroit Region | 29 |  | 41
J 904426 | Texas Region | 29 |  | 41
J 904426 | St. Louis Region | 29 |  | 41
J 904426 | Seattle Region | 30 |  | 42
J 904426 | New York Region | 30 |  | 42
J 904426 | California Region | 30 |  | 42

## E. Timeline for Funds
System Name | System ID | Pre-Auction Costs ($M) | Pre-Auction Transfer Requested ($M) | Pre-Auction Costs Incurred between 6-28-2010 and 2-22-2012 | Equipment-Related Costs ($M) | Deployment-Related Costs ($M) | Total Cost for System ($M) | Begin Expenditure of Funds | End Expenditure of Funds | Costs Associated with Expanded Capability | Description of Expanded Capability | Explanation/ Justification
Mobile | DOJ -1 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | Microwave
Birmingham | DOJ -2 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | TRR
Phoenix | DOJ -3 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | ACTS
San Diego | DOJ -4 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | PGM
Baltimore1 | DOJ -5 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | Video
Baltimore2 | DOJ -6 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | TT&C
Jacksonville | DOJ -7 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | Telemetry
Miami | DOJ -8 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | Robotics
New Orleans | DOJ -9 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | UAS
Detroit | DOJ -10 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems | Other
Minnesota | DOJ -11 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Buffalo | DOJ -12 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Oklahoma City1 | DOJ -13 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Oklahoma City2 | DOJ -14 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Portland1 | DOJ -15 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Portland2 | DOJ -16 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Knoxville | DOJ -17 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Houston | DOJ -18 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Dallas | DOJ -19 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Washington, DC | DOJ -20 |  |  |  | 0.15 |  | 0.15 | 3 | 30 |  |  | Relocation of Systems
Operational1 | DOJ -21 |  |  |  | 3.96 |  | 3.96 | 3 | 30 |  |  | Relocation of Systems
Operational2 | DOJ -22 | [5 empty] | NA | 3 | 30 |  |  | Relocation of Systems
Surveillance1 | DOJ -23 | 2.221 | 2.221 | 0 | 462.429 | 106.247 | 570.897 | 3 | 96 | 15.95 | see Tab H 7 | Relocation of Systems
Surveillance2 | DOJ -24 | [5 empty] | NA | 3 | 96 |  |  | Relocation of Systems
Surveillance3 | DOJ -25 | [5 empty] | NA | 3 | 96 |  |  | Relocation of Systems
Operational3 | DOJ -26 |  |  |  | 8.086 |  | 8.086 | 3 | 30 |  |  | Relocation of Systems
Operational4 | DOJ -27 | [5 empty] | NA | 3 | 30 |  |  | Relocation of Systems
Operational5 | DOJ -28 | [5 empty] | NA | 3 | 30 |  |  | Relocation of Systems
Operational6 | DOJ -29 | [5 empty] | NA | 3 | 30 |  |  | Relocation of Systems
Operational7 | DOJ -30 | [5 empty] | NA | 3 | 30 |  |  | Relocation of Systems
Surveillance4 | DOJ -31 |  |  | 0 | 179.316 | 53.0213 | 232.3373 | 3 | 96 | 3.05 | see Tab H 7 | Relocation of Systems
Surveillance5 | DOJ -32 | [5 empty] | NA | 3 | 96 |  |  | Relocation of Systems
Surveillance6 | DOJ -33 |  |  | 0 | 252.295 | 33.755 | 286.05 | 3 | 96 | 3.98 | see Tab H 7 | Relocation of Systems
TOTAL | [6 empty] | 1104.3303 |  |  | 22.98
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!

## F. NTIA Interactions
Interaction required with NTIA to implement this Transition Plan
1 | New frequency assignments in the GMF are required to be approved by NTIA by 12/31/2014 in the S and C Bands. This includes US&Ps throughout 2200 - 2290Mhz, 4400 - 4500 and 4600 - 4900 to include Band Assignments if required by NTIA.
2 | New frequency assignments in the GMF will be required to be approved by NTIA by 12/31/2014 in the L Band. This also includes assignments for a central receive control channel in each metropolitan area.
3 | New Point to Point frequency assignments in GMF will be required in 8100 - 8500Mhz.
4 | NTIA assistance with Commercial Carriers regarding their proposed dramatic increase in commercial services costs for Mobile Broadband is required.

## G. Excluded Information
Serial Number | Description of Classified or Sensitive Information | Reason for Exclusion | Reference
J 052221 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act | Classified
J 053257 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act | Sensitive
J 062013 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 042278 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 042201 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 053717 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 062689 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 073001 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 042351 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 062575 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 042307 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 064554 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 052207 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 052208 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 053308 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 062594 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 053700 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 043969 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 053791 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 042229 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 032216 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 991007 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 951326 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 055907 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 055908 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 114544 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 114546 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 112602 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 112599 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 112600 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 039004 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 071082 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act
J 904426 | Freq, Emission Bandwidth, TX and RX Lat/Long, Bureau | Sensitive | DOJ 2620.7 CONTROL AND PROTECTION OF LIMITED OFFICIAL USE INFORMATION & The Freedom of Information Act

## H. Factors
| Factor | Impact on Fulfillment of Transition Plan
1 | Pre Auction Funds | It is assumed that Pre Auction Funds will be available in FY-14 for Pre Auction Planning of several key initiatives of the DOJ relocation strategy. Pre auction planning is crucial to the deployment timing of Adaptive Central Receive System and its associated components.
2 | Classified or Sensitive Information that is not releasable to the public is included in the Transition Plan. | The redacted information will not impede fulfillment of the transition plan
3 | Alternate Frequency Assignments | L Band = 1780-1850 MHz, C Band = 4400-4940 MHz, X Band = 8100-8500 MHz, S Band = 2200-2290 MHz
4 | Tab D , Vacate Assignment Column | Dates are dependant on DOJ receipt of funds by May 2015
5 | Tab E, Begin and End Expenditure of Funds Columns | Dates are dependant on DOJ receipt of funds by May 2015
6 | Tab E, Expenditure of Funds beyond Vacate Spectrum Date | Funding is required beyond the Spectrum Vacate Date in order to build out the nationwide Adaptive Central Receive System and associated components
7 | Tab E, Expanded Capability Costs | *****
8 | Commercial Broadband Costs | The Commercial Broadband cost estimates are based on our ability to accurately estimate the future costs of broadband services. Existing contracts expire in 2014. At this time, this risk is rated as medium.
9 | Vendor Costs and Schedule | The plan is dependent on vendors being able to meet DOJs estimated costs and schedules. At this time, this risk is rated as low.
10 | Adjustments To Base Budget | Reductions to the original DOJ Transition Plan were made at the request of the Technical Panel, including transitioning recurring costs beyond three years to annual Adjustments To Base Budget (ATB). This increases the risk for this transition plan because it now relies upon ATB during the deployment phase for success. At this time, this risk is rated as high.
11 | DOJ Cost Reduction Risk | The Department of Justice’s (DOJ) revised transition plan includes an estimated total transition cost of $1.1 billion for planning and auction scoring purposes. This $1.1 billion estimate may increase or decrease based on continued review, including the results from a third-party cost review that will begin within the next few weeks. The execution of the funding may also shift during the transition implementation. The Department has worked closely with the Technical Panel to address questions and revise our transition plan based on Technical Panel direction, including changing the structure of recurring costs, eliminating a DOJ contingency reserve, and accepting a certain level of risk, particularly related to commercial service costs and potential price inflation. To reach the planning estimate of $1.1 billion, the Department has reduced its cost estimate by approximately $72 million in commercial services and $93 million in other areas from its most recent estimate of $1.265 billion. Overall, the Department has cut over $524 million from its initial transition estimate of $1.624 billion in order to meet the $1.1 billion planning estimate. The Department’s top priority is to ensure that law enforcement agencies do not lose surveillance capability after the AWS-III auction. This plan maintains comparable operational capability, but we are concerned that any further reductions, pending the third-party review, will compromise the ability of the Department to carry out its mission, including criminal investigations and national security matters. The Department will continue to review its cost estimates through the pending independent review and will revise the cost estimates based on the outcome of that review.
12 | Temporary Sharing Stipulation | For each of the frequency entries within Tab C that are labeled as “Vacate With Temp”, the following stipulation applies: The concept of “temporary sharing” is subject to several conditions and these include: coordination requests will be addressed on a site-by-site basis and sharing conditions shall be approved by DOJ; sharing consideration will be assessed based on industry build-out/deployment plans and incumbent DOJ operations; and a recognition that industry be aware that sharing may be assessed as not feasible for an extended period of time. Industry should not assume that a label of “Vacate With Temp” indicates that sharing for that frequency is in any way assured. The label only means that DOJ is agreeable to determine if sharing is feasible in response to individual industry coordination requests. As noted in Tab D of this transition plan, in the "Begin Temporary Sharing" column, DOJ will begin discussions and coordination of sharing 12 months prior to the "Vacate Assignment" dates listed in Tab D.

## I. Additional Information
WASHINGTON DC REGION | FLORIDA REGION | NORTHEAST REGION | ATLANTA REGION | CHICAGO REGION | NEW ORLEANS REGION
Baltimore | Jacksonville | Boston | Atlanta | Chicago | Birmingham
Washington | Miami | New Haven | Charlotte | Indianapolis | Jackson
Norfolk | San Juan | Newark | Columbia | Milwaukee | Little Rock
Richmond | Tampa | Philadelphia | Knoxville | Minneapolis | Mobile
| Orlando | Pittsburgh | Memphis | Springfield | New Orleans
|  |  | Nashville | St Paul
Raleigh
Economic Areas | Economic Areas | Economic Areas | Economic Areas | Economic Areas | Economic Areas
13 Washington-Baltimore | 29 Jacksonville | 3 Boston-Worcester-Lawrence-Lowell-Brockton | 18 Greensboro-Winston-Salem-High Point | 59 Green Bay | 36 Dothan
14 Salisbury | 30 Orlando | 12-Philadelphia-Wilmington-Atlantic City | 19 Raleigh-Durham-Chapel Hill | 63 Milwaukee-Racine | 90 Little Rock-North Little Rock
15 Richmond-Petersburg | 31 Miami-Ft Lauderdale | 9 State College | 21 Greenville | 60 Appleton-Oshkosh-Neenah | 76 Greenville
20 Norfolk-Virginia Beach-Newport News | 32 Fort Myers-Cape Coral | 11 Harrisburg-Lebanon-Carlisle | 22 Fayetteville | 66 Fort Wayne | 77 Jackson
16 Staunton | 33 Sarasota-Bradenton | 53 Pittsburgh | 23 Charlotte-Gastonia-Rock Hill | 67 Indianapolis | 82 Biloxi-Gulfport-Pascagoula
17 Roanoke | 34 Tampa-St. Petersburg-Clearwater | 54 Erie | 24 Columbia | 68 Champaign-Urbana | 83 New Orleans
| 35 Tallahassee | 4 Burlington | 25 Wilmington | 64 Chicago-Gary-Kenosha | 84 Baton Rouge
| 81 Pensacola | 1 Bangor | 26 Charleston-North Charleston | 65 Elkhart-Goshen | 85 Lafayette
| 174 Puerto Rico and US Virgin Islands |  | 27 Augusta-Aiken | 69 Evansville-Henderson | 86 Lake Charles
| 176 Gulf of Mexico |  | 28 Savannah | 97 Springfield | 88 Shreveport-Bossier City
|  |  | 37 Albany | 107 Minneapolis-St Paul | 89 Monroe
|  |  | 38 Macon | 109 Duluth-Superior | 74 Huntsville
|  |  | 39 Columbus | 101 Peoria-Pekin | 75 Tupelo
|  |  | 40 Atlanta | 102 Davenport-Moline-Rock Island | 78 Birmingham
|  |  | 41 Greenville-Spartanburg-Anderson | 103 Cedar Rapids | 79 Montgomery
|  |  | 42 Asheville | 104 Madison | 80 Mobile
|  |  | 43 Chattanooga | 105 La Crosse | 91 Fort Smith
|  |  | 44 Knoxville | 106 Rochester | 92 Fayetteville-Springdale-Rogers
|  |  | 45 Johnson City-Kingsport-Bristol | 108 Wausau | 95 Jonesboro
|  |  | 46 Hickory-Morganton | 110 Grand Forks
|  |  | 71 Nashville | 111 Minot
|  |  | 73 Memphis | 112 Bismarck
113 Fargo-Moorhead
DETROIT REGION | TEXAS REGION | ST LOUIS REGION | SEATTLE REGION | NEW YORK REGION | CALIFORNIA REGION
Cincinnati | Oklahoma City | Kansas City | Anchorage | Albany | Honolulu
Cleveland | Dallas | Omaha | Portland | Buffalo | Las Vegas
Detroit | Albuquerque | St. Louis | Seattle | New York | Los Angeles
Louisville | El Paso | Denver |  |  | Sacramento
Columbus | Houston | Salt Lake City |  |  | San Francisco
| San Antonio |  |  |  | San Diego
| Phoenix |  |  |  | Oakland
Tucson
Austin
Economic Areas | Economic Areas | Economic Areas | Economic Areas | Economic Areas | Economic Areas
47 Lexington | 87 Beaumont-Port Arthur | 96 St Louis | 2 Portland | 5-Albany-Schenectady-Troy | 151 Reno
49 Cincinnati-Hamilton | 127 Dallas-Ft Worth | 93 Joplin | 144 Billings | 6 Syracuse | 153 Las Vegas
50 Dayton-Springfield | 128 Abilene | 94 Springfield | 145 Great Falls | 7-Rochester | 160 Los Angeles-Riverside-Orange County
51 Columbus | 129 San Angelo | 98 Columbia | 146 Missoula | 8-Buffalo-Niagara Falls | 161 San Diego
55 Cleveland-Akron | 130 Austin-San Marcos | 99 Kansas City | 147 Spokane | 10 New York-No. New Jersey-Long Island | 162 Fresno
56 Toledo | 131 Houston-Galveston-Brazoria | 100 Des Moines | 167 Portland-Salem |  | 163 San Francisco-Oakland-San Jose
57 Detroit-Ann Arbor-Flint | 132 Corpus Christi | 114 Aberdeen | 168 Pendleton |  | 164 Sacramento-Yolo
58 Northern Michigan | 133 McAllen-Edinburg-Mission | 115 Rapid City | 169 Richland-Kennewick-Pasco |  | 165 Redding
61 Traverse City | 134 San Antonio | 116 Sioux Falls | 170 Seattle-Tacoma-Bremerton |  | 172 Honolulu
62 Grand Rapids-Muskegon-Holland | 135 Odessa-Midland | 117 Sioux City | 171 Anchorage |  | 173 Guam and Northern Mariana Islands
70 Louisville | 136 Hobbs | 119 Lincoln | 166 Eugene-Springfield |  | 175 American Samoa
48 Charleston | 137 Lubbock | 120 Grand Island
52 Wheeling | 138 Amarillo | 121 North Platte
72 Paducah | 139 Santa Fe | 122 Wichita
| 124 Tulsa | 123 Topeka
| 125 Oklahoma City | 140 Pueblo
| 126 Western Oklahoma | 141 Denver-Boulder-Greeley
| 150 Boise City | 118 Omaha
| 154 Flagstaff | 148 Idaho Falls
| 156 Albuquerque | 149 Twin Falls
| 157 El Paso | 152 Salt Lake City-Ogden
| 158 Phoenix-Mesa | 142 Scottsbluff
| 159 Tucson | 143 Casper
155 Farmington